## Action
Action Id | Item | Effort Level | Urgency | Summary | Lead | What to Do | Expected Completion | Actual Completion | Deliverable Usage
GWG.2016.2b.1 | web meeting |  |  | GCC to set up GRWG/GDWG web meeting on instrument performance monitoring. | GCC | Configuration | 2017-annual metting
GRWG.2016.2d.1 |  |  |  | Tim & Dohyeong to review outstanding actions on Tim Hewison and decide which to transfer to GRWG Chair. | Dohyeong, Tim | Analysis | 2017-annual metting
GRWG.2016.2j.1 |  |  |  | Tim to share housekeeping link for IASI monitoring | EUM(Tim) | Information | 2017-annual metting
GRWG.2016.2k.1 |  |  |  | CMA to report at the 2017 annual meeting about the comparison in the RSB of the various instruments. | CMA | Analysis | 2017-annual metting
GWG.2016.2m.1 |  |  |  | GCC to contact IMD and coordinate interactions re: sharing and implementing GEO-LEO code. | GCC | Information | 2017-annual metting
GVNIR.2016.2n.1 | GSICS products with INSAT-3D |  |  | Dave to provide MODIS data to ISRO to perform inter-calibration using DCC. | NASA(Dave) | Information | 2017-annual metting
GWG.2016.2t.1 | Naming convention of GSICS products |  |  | GCC (Manik to coordinate) to develop a prototype template for product landing pages to be linked to the GSICS product catalog. | GCC(Manik) |  | 2017-annual metting
GWG.2016.2u.1 | GSICS Procedure for Product Acceptance |  |  | GCC to coordinate input from product creators/developers to identify the family of monitored and reference instruments their product is applicable to. | GCC |  | 2017-annual metting
GIR.2016.3c.1 | GEO-Ring dataset analysis |  |  | Rob to consider including an analysis of GEO-ring bias monitoring statistics provided by ECMWF as part of IOGEO. | EUM(Rob) | Analysis | 2017-annual metting
GIR.2016.3c.2 | GEO-Ring dataset analysis |  |  | EUMETSAT to coordinate input for GEO-ring test dataset from all geostationary satellite operators | EUM(Rob) |  | 2016-09-01
GIR.2016.3e.1 | Selecting GSICS References: IR, VIS and MW(revising terminology) |  |  | Tim Hewison to consider revising terminology used in the current “Primary GSICS Corrections”, during demonstration phase. | EUM(Tim) | Configuration | 2017-annual metting
GIR.2016.3n.1 | Handling Diurnal Cycle in GEO-LEO IR |  |  | Fred to report at next meeting on cooperation with KMA on black body calibration correction. | NOAA(Fred) | Analysis | 2017-annual metting
GIR.2016.3o.1 | v2 of GEO-LEO IR - alternative ATBDs(cold end corrections effect) |  |  | Arata to check how the cold end corrections are behaving using AIRS. | JMA(Arata) | Analysis | 2017-annual metting
GIR.2016.3o.2 | v2 of GEO-LEO IR - alternative ATBDs (regression model and correction) |  |  | Arata to use the various regression methods for both radiance and brightness temperatures and process the corrections as derived from AIRS and report back. | JMA(Arata) | Analysis | 2017-annual metting
GIR.2016.3p.1 | Hyperspectral IR comparisons - including TANSO-FTS/2 – 17:05 |  |  | Rose to communicate the constraints for Metop-A end-of-life activities. Can we accommodate additional manoeuvres? | EUM(Rose) |  | 2017-annual metting
GIR.2016.3p.2 | Hyperspectral IR comparisons - including TANSO-FTS/2 – 17:05 |  |  | CrIS team (POC: Likun) to work on the inter-comparison between CrIS and TANSO-FTS and report back to GRWG. | CrIS team(Likun) | Analysis | 2017-annual metting
GIR02016.3p.3 | Hyperspectral IR comparisons - including TANSO-FTS/2 – 17:05 |  |  | EUM + CNES (POC: Denis Jouglet (CNES) and Dorothee Coppens (EUM)) to work on the inter-comparison between CrIS and TANSO-FTS. | EUM(Dorothee), CNES(Denis) | Analysis | 2017-annual metting
GIR.2016.3p.4 | Hyperspectral IR comparisons - including TANSO-FTS/2 – 17:05 |  |  | JAXA to provide info about TANSO FTS sampling (POC: Kei Shiomi) | JAXA(Kei) | Information | 2017-annual metting
GIR.2016.3q.1 | IR Reference Sensor Traceability and Uncertainty(monitoring CrIS, IASI) |  |  | Likun Wang to coordinate a team to continue to monitor CrIS, IASI and AIRS and report to GSICS. | NOAA(Likun) | Configuration | 2017-annual metting
GIR.2016.3r.1 | SRF Retrievals |  |  | Manik to circulate draft manuscript on SRF retrieval method | NOAA(Manik) | Information | 2017-annual metting
GIR.2016.3s.1 | CLARREO preparations |  |  | Dave Tobin to repeat inter-calibration uncertainty analysis for CLARREO PATHFINDER on ISS and report. | CLARREO group (Dave Tobin) | Analysis | 2017-annual metting
GRWG.2016.3s.2 | CLARREO preparations |  |  | GRWG Chair to check the interest and availability of key representatives for a workshop on hyperspectral instruments as inter-calibration references. | GRWG Chair | Configuration | 2017-annual metting
GVNIR.2016.4a.1 | lunar calibration and Earth View discrepancy |  |  | Aisheng and Tom to interact in order to investigate the discrepancy between the lunar calibration results and the Earth View results on both Terra and Aqua MODIS. | NASA(Aisheng), JAXA(Tom) |  | 2017-annual metting
GVNIR.2016.4a.2 | MODIS calibration |  |  | Tom Stone to contact NASA (POC: Jim Butler) about the possibility of extending the USGS analysis of MODIS lunar observation data to study the divergence of sensor responses exhibited by lunar and solar diffuser/vicarious calibration techniques. | USGS(Tom) |  | 2017-annual metting
GVNIR.2016.4d.1 | ROLO developments & schedule |  |  | GSICS/WMO to provide a support letter for the ARCSTONE mission. | GSICS/WMO |  | 2017-annual metting
GVNIR.2016.4f.1 | Status of GIRO policy, infrastructure & inter-cal study |  |  | Seb to verify that the policy reflects the needs of an Agency implementing a modification to the GIRO to ensure it is assessed against the benchmark. | EUM(Seb) |  | 2017-annual metting
GVNIR.2016.4h.1 | Lunar surface target selections & auto-mapping |  |  | Bertrand to investigate if this is possible for CNES to provide NOAA with Pleiades Moon data in order to support the characterization of uniform target sites. | CNES(Bertrand) |  | 2017-annual metting
GVNIR.2016.4h.2 | Lunar surface target selections & auto-mapping |  |  | NOAA and EUMETSAT to liaise for comparison with time series of MSG full disk Moon irradiance measurements over same time period. NOAA to report back in one year time. | NOAA, EUM |  | 2017-annual metting
GVNIR.2016.4n.1 | Progress toward DCC Demo product |  |  | Dave will work with KMA to implement the GSICS DCC process to promote KMA to demonstration product. | NASA(Dave) | Analysis | 2017-annual metting
GVNIR.2016.4o.1 | Progress toward DCC Demo product |  |  | Dave to provide information on Aqua MODIS for GOES instruments. | NASA(Dave) | Information | 2017-annual metting
GVNIR.2016.4p.1 | Discussion Outstanding issues on DCC algorithm, Demo products & GPPA, Journal article |  |  | Dave to coordinate the writing of a paper on the GSICS DCC GEO-LEO algorithm. | NASA(Dave) |  | 2017-annual metting
GWG.2016.7b.1 | Strawman User Requirements’ document |  |  | GCC to coordinate input from GPRCs to attempt to identify at least one user for NRT, RAC and climate applications and interact with users to establish draft user requirements. (note: this will provide input to Action EP_GRWG_16.10). | GCC |  | 2017-annual metting
GIR.2016.7b.2 | Strawman User Requirements’ document |  |  | Tim Hewison to resolve use of GSICS products for Meteosat IR with FIDUCEO. | EUM(Tim) |  | 2017-annual metting
GVNIR.2016.7d.1 | GRWG Summary and Agree Actions |  |  | NASA(Dave) to work with KMA for KMA to enter DCC demo-phase. | NASA(Dave) |  | 2017-annual metting
GVNIR.2016.7d.2 | GRWG Summary and Agree Actions |  |  | Dave to contact IVOS Chair and ACC to coordinate a recommended update to reference solar spectrum to convert from radiance to reflectance by setting up web meeting. | NASA(Dave) |  | 2017-annual metting
GRWG.2016.7f.1 | Workshop on best practices on pre-flight and onboard calibration |  |  | Tim/Rob (EUM) to forward draft requirements for pre-launch characterisation to WMO. | EUM(Tim/Rob) | Information | 2017-annual metting | Closed by email 2016-03-09
GVNIR.2016.7h.1 | Interaction & 2016 Users Workshop |  |  | Seb to provide supporting slides to Dave Doelling as chair of the VIR/NIR sub-group to be presented at the Users’ WS (upon availability of the feedback from Marine Application). | EUM(Seb) | Information | 2017-annual metting
GWG.2016.7h.2 | Interaction & 2016 Users Workshop |  |  | Larry to coordinate with the JPSS meeting organisers to organise a dedicated time-slot for the GSICS Users’ WS optimising attendance and promote through meeting agenda. | GCC(Larry)
GWG.2016.7h.3 | Interaction & 2016 Users Workshop |  |  | GCC to check the possibility to have remote access through WebEx | GCC
GVNIR.2016.7i.1 | Topics & Chairing next Web Meetings |  |  | Dave to contact Nigel about joint web meeting. | NASA(Dave) | Contact | 2017-annual metting
GVNIR.2016.7i.2 | Topics & Chairing next Web Meetings |  |  | Seb to rescope the web meeting on lunar calibration. | EUM(Seb) |  | 2017-annual metting
GIR.2016.7i.3 | Topics & Chairing next Web Meetings |  |  | Tim to contact Sasha regarding the opportunities using NWP bias monitoring statistics. | EUM(Tim) | Contact | 2017-annual metting
GWG.2016.7i.4 | Topics & Chairing next Web Meetings |  |  | GCC to add a webex meeting for a user feedback (? probably not needed). Or organise one on changing reference and ensure traceability (to be organised by Dave) . | GCC | Configuration | 2017-annual metting
GVNIR.2016.7i.5 | Topics & Chairing next Web Meetings |  |  | Dave to provide EUMETSAT with VIIRS data to generate inter-calibration of all SEVIRI warm channels using the DCC method. | NASA(Dave) |  | 2017-annual metting
GVNIR.2016.7i.6 | Topics & Chairing next Web Meetings |  |  | Dave to organise a web meeting about the publication on DCCs. | NASA(Dave) |  | 2017-annual metting
GDWG.2016.7j.1 | Date & Place of Next WG Meetings |  |  | Peter to set-up a template for the agency report, which would help focusing on GSICS activities. | EUM(Peter) | Configuration | 2017-annual metting
GWG.2016.7j.2 | Date & Place of Next WG Meetings |  |  | GCC (Larry) to contact NIST to organise the next GRWG/GDWG annual meeting. | GCC(Larry)
GWG.2016.7j.3 | Date & Place of Next WG Meetings |  |  | Dave to contact D. Tobin (CLARREO group) to check the possibility to organise the meeting in NOAA, Madison. | NASA(Dave) |  |  | closed 2016-03-08

## Recommendation
Agenda Id | Item | Effort Level | Urgency | Summary | Lead | What to Do | Expected Completion | Actual Completion | Deliverable Usage
1k | Himawari-8 Ocean Color and Aerosol |  |  | JAXA to continue to collaborate with JMA to define requirements for GSICS Corrections for AHI ocean colour and aerosol products. | JAXA |  | 2017-annual metting
1l | Impact of GSICS Correction on Himawari-8 SST |  |  | GSICS IR sub-group to develop LEO-LEO GSICS corrections. | GSICS IR group |  | 2017-annual metting
1t | Intercalibration on the FY3/MWRI |  |  | CMA to consider using the SSMIS CDR at Colorado State University that is available and that would be of better quality in their analysis of MWRI data. | CMA |  | 2017-annual metting
2c | GDWG report |  |  | GDWG to provide guidance for code sharing in order to avoid problem with licensing (TBConfirmed) | GDWG
2j | Metop-A maneuver as part of End of Life planning |  |  | EUM to consider pitch-over maneuver of Metop-A as part of End of Life planning, to characterise instruments’ space views and scan angle dependences, and introducing a precessionary orbit to allow the instruments to sample more of the diurnal cycle. (Post-meeting note: This was raised at the EUMETSAT STG-SWG meeting, where EUMETSAT were requested to consider this, but noted that it is only possible to drift the orbit slowly, given fuel constraints.) | EUM |  | 2017-annual metting
2j | Lunar Observation |  |  | CMA to consider coordinating Simultaneous Lunar Observations from ground-based sensors to coincide with satellite observations. | CMA |  | 2017-annual metting
2o | non-linearity in the COMS WV channel |  |  | KMA to investigate effects of the non-linearities in the COMS WV channel. | KMA | Analysis | 2017-annual metting
2u | GSICS Procedure for Product Acceptance |  |  | the product generator applying the same algo to different instruments should be able to move directly to pre-operational mode subject to reviewing the uncertainty analysis. |  |  | 2017-annual metting
3d | NASA SBAF Tool - including hyperspectral deserts |  |  | EUM to further investigate potential to shift UVN FOV southwards during commissioning and/or winter time – and seek agreement from GRWG whether this would support GSICS activities (SBAF, desert site characterisation). If so, invite WMO to send a letter of support. | EUM |  | 2017-annual metting
3h | Plans for AVHRR inter-calibration |  |  | EUMETSAT to liaise with SCIAMACHY team to investigate difference between the 2 instruments (GOME-2 and SCIAMACHY) using SNOs. | EUM | contact | 2017-annual metting
3j | GEO-LEO IR Progress at ISRO |  |  | ISRO to contact Peter Miu to set up a standing order + submit user request through the EUM helpdesk. | ISRO | contact | 2017-annual metting
3k | GEO-LEO IR Progress at JMA |  |  | NOAA-JMA to corporate to resolve GEO-LEO IR scan dependency. | NOAA, JMA |  | 2017-annual metting
3k | AHI's diurnal variation |  |  | JMA to share their analysis of AHI’s diurnal variation during commissioning phase to GSICS user workshop. | JMA | Information | 2017-annual metting
3l | GEO-LEO IR Progress at KMA |  |  | KMA to assess uncertainties in double differences between COMS-1/MI and IASI-A and -B (e.g. as standard error) | KMA | Analysis | 2017-annual metting
3p | Hyperspectral IR comparisions |  |  | Although there were different opinions, representing different users’ interested, the majority of participants favoured the opinion that there is not really a benefit in changing IASI-A as it is reaching its end of life. Instead, IASI-B should be updated asap to take advantage of the overlap to check the impact and improve IASI-B till its end-of-life, noting that the overlap is crucial to characterise the impact of the change. Of course, changes should be applied to IASI-C. |  |  | 2017-annual metting
3q | IR Reference Sensor Traceability and Uncertainty |  |  | Define common spectral (boxcar) regions for comparisons. |  |  | 2017-annual metting
3q | IR Reference Sensor Traceability and Uncertainty |  |  | Member of AIRS team to be involved in monitoring differences wrt IASI and CrIS. | AIRS team |  | 2017-annual metting
3r | SRF Retrievals |  |  | Manik to apply SRF retrieval to CO2 or water vapour channels | NOAA(Manik) |  | 2017-annual metting
3r | SRF Retrievals |  |  | Manik to check how many singular vectors are greater than 1 in SRF retrieval. | NOAA(Manik) |  | 2017-annual metting
3r | SRF Retrievals |  |  | Manik to evaluate uncertainties on the SRF retrieval. | NOAA(Manik) |  | 2017-annual metting
3t | Development of LEO-LEO IR Products |  |  | NASA is encouraged to follow the approach adopted for the GEO-LEO IR to derive GSICS products. | NASA |  | 2017-annual metting
3t | calibration of MODIS and VIIRS cold-end |  |  | NASA to investigate the relative calibration of MODIS and VIIRS cold-end. | NASA |  | 2017-annual metting
4b | VIIRS calibration summary presentation |  |  | Users should avoid the first year of data from of S-NPP/VIIRS |  |  | 2017-annual metting
4d | ROLO developments & schedule |  |  | JMA and USGS to work together on AHI data in support of ROLO development. | JMA, USGS |  | 2017-annual metting
4e | Application of GIRO to NIR bands |  |  | JMA is strongly encouraged to keep shared their data with the lunar calibration community as those data would greatly help in characterising phase dependency spectrally. It would help the community to achieve intercalibration for sensors with similar bands. | JMA |  | 2017-annual metting
4g | Discussion - Way forward on lunar inter-calibration |  |  | CNES and EUM to resolve any differences in formulation of presented lunar inter-calibration approaches. | CNES, EUM |  | 2017-annual metting
4h | Lunar surface target selections & auto-mapping |  |  | NOAA to interact with JMA to understand the root cause of the differences between analyses (in particular wrt deep space counts). | NOAA |  | 2017-annual metting
7e | GDWG summary and Agree Actions |  |  | GSICS decisions should be represented to EP for information or endorsement if needed. AND DOCUMENTED.

## Decision
Agenda ID | Item | Effort Level | Urgency | Summary | Lead | What to Do | Expected Completion | Actual Completion | Deliverable Usage
2s | Defining GSICS Products, Deliverables, Maturity |  |  | Static instrument information should be provided on Instrument Information landing pages, linked from OSCAR. GSICS should focus on provided updates on dynamic aspects of performance.
3c | Discussion: GEO-Ring dataset analysis |  |  | The best full disk coverage within 30 min time difference should be provided for the GEO-ring demonstration dataset
3c | Discussion: GEO-Ring dataset analysis |  |  | The format of the dataset can be defined in a free choice by provider, but preferably netCDF/HDF. Otherwise, a reader should be provided.
3f | monitoring the double differences between references |  |  | It was agreed that there is a need for monitoring the double differences between references instruments during the overlap periods.
3o | v2 of GEO-LEO IR - alternative ATBDs |  |  | JMA should include the functions and coefficients need to convert between digital counts and radiance in the netCDF format of their AHI products.
7d | GRWG Summary and Agree Actions |  |  | GPRCs to decide update frequency for GSICS products, aiming to provide users with most frequent updates with uncertainty meeting their own requirements.