## Slide 1: GSICS Actions 2019-2020
Manik Bali and Lawrence E. Flynn
GDWG Webmeeting, 3/15/2020

## Slide 2
Outline
Action Status
Review of Actions
Possible topics for meetings to come

## Slide 3: Action Status
GVISNIR: Actions are from webmeeting of 12102019
GCC: Three Actions can be combined into 1
Chart: Action 2019 Status
| GRWG | GDWG | GWG | GIR | GMW | GVNIR | GUV | GCC
Open | 17 | 15 | 16 | 15 | 14 | 4 | 3 | 6
Closed | 1 | 18 | 0 | 0 | 0 | 0 | 0 | 4

## Slide 4
Action Sheet
https://www.star.nesdis.noaa.gov/smcd/GCC/MeetingActions.php
Review of Actions ( Closed and Active)

## Slide 5
Action ID |  | Action Descrition
A.GWG.20200122.2 | http://gsics.atmos.umd.edu/bin/view/Development/20200122 | Fangfang Yu (NOAA) to propose revised Annual Calibration Report and provide as a template
A.GWG.20200122.2 | http://gsics.atmos.umd.edu/bin/view/Development/20200122 | Fangfang Yu (NOAA) to propose revised Annual Calibration Report and provide as a template
A.GWG.2019.10l.1 |  | Dohyeong Kim (KMA) to plan to host GRWG/GDWG meeting in March 2020.
A.GWG.2019.10l.2 |  | Odele Coddington (LASP) to consider hosting GRWG/GDWG in 2021.
A.GWG.2019.5p.1 |  | Mitch Goldberg (NOAA) to propose an international cooperation on sea ice products to CGMS

## Slide 6: Discussions at EP-21
Action ID |  | Action Description
A.GCC.2019016.3 |  | Obtain QA4E0 for acceptance criterion of GSICS Deliverables (Dave)
A.GCC.20190516.1 |  | GCC to relax User Guide requirement and uncertainty for GSICS Products, if measurements come from operational maturity.
A.GDWG.20190516.1 |  | GDWG Chair to request CGMS Task Force on Satellite Data and Codes to review a proposal of adding SRF to International Data Subcategory of Common Table C-13 of WMO Manual on Codes for a coordination with WMO IPET-CM.
A.GDWG.20190516.3 |  | GDWG Chair to develop a procedure on updating Annual GSICS Calibration Report.
A.GEP.20190517.2 |  | EP Chair to coordinate with WIGOS to enhance collaboration to integrate GSICS into WIGOS.
A.GEP.20190517.1 |  | EP Chair to coordinate with WIGOS for utilizing GSICS Product Catalog with Quicklooks in WDQM system.

## Slide 7: Followup Actions/topics/Meeting
Experience of using GSICS products
    Feedbacks from Andy, Viju, Manik and community
Do we need a new class of products with more information?
Inter-operability between observing systems
  Integration to WIGOS ( Talk in MW Session, WIGOS platform)

## Slide 8
Conclusion