## Updated
Action # | Task Name | Lead | Description | Deliverable | Q1 2011 | Q2 2011 | Q3 2011 | Q4 2011 | 2012 Q1
| Governance |  | Progress meetings, reporting and action tracking
GIP 1.2-1.3 | Executive Panel Meeting | EP | Provide the GSICS program guidelines | Meeting report
GIP 5.5 | GRWG/GDWG Joint Meeting | GDWG/GRWG | Resolving related data and science issues | Meeting report
GRWG05_10R | Joint GDWG and GRWG meeting site decision | EP | Select from candidate venues to host the next GRWG/GDWG meeting | Report
GIP 5.5 | GRWG Web Meeting | GRWG | Support GSICS by resolving related scientific issues | Meeting report
GRWG05_21 | GRWG Web Meeting Organization | GRWG Chair | Organise GRWG web meetings by at least 2 weeks beforehand | Meeting announcement
GIP 5.5 | GDWG Web Meeting | GDWG | Support GSICS by resolving related data management issues | Meeting report
GIP 2.02 | GSICS Operating Plan | GCC | Update GSICS Operating Plan | Updated Operations Plan
EP06_15 | GSICS Operating Plan | WMO+GCC | R. Iacovazzi and J. Lafeuille to finalize the updated operations plan for publication on the GSICS web site. | Finalized Operations Plan
EP08_10 | Documentation Plan | WMO | WMO (J. Lafeuille) to circulate a draft revised documentation plan with more detailed contents of each document, as a prerequisite for developing these documents. | Revised Documentation Plan distributed
EP08_15 | Bi-weekly Teleconference | EP Chair | The Chairman (M. Goldberg) and Secretariat (J. Lafeuille) to set-up a bi-monthly Executive Panel teleconference. | Telecon
| Enhancing Outreach and User Interaction |  | Inform GSICS community & beyond and seek feedback
GIP 2.11 | Quarterly Newsletter | GCC | Inform members and stake-holders | Newsletter delivered electronically
EP08_01 & GIP2.1 | Update web sites | All | WMO, GCC, and all GPRCs to update GSICS web sites, presentation slides, fact sheets, to include reference to all Members, observers and partners. | Updated web sites
GDWG04_07 | Evaluation of WMO GSICS Web Site | EUMETSAT | Look into the improvements needed to address the observations on the current WMO’s site structure - e.g., legibility of the GSICS logo (coordinate with all the GPRCs on how this can be done). | Briefing of recommended site updates to EP and then to WMO for upload
GDWG04_08 | Discuss information content on GPRC home pages | EUMETSAT | Discuss with the GDWG on what common information shall be shown on the GPRC home pages. | Meeting
GDWG04_10R | Updates of GPRC Web Sites | All GPRC's | Each GPRC shall provide a home page describing what they do. They shall ensure the page is easily identified as a GSICS Web page, e.g. apply GSICS standard logo, and look and feel. Compose common text informing the reader about the information on the GPRC (Contribution to GSICS as a GPRC, regularly providing comparable data sets etc. | Web site updates
GDWG03_16 and GDWG04_03R | GSICS Portal | GCC | GCC to make a start on preparing a specification document to capture the requirements for a GSICS Web Portal | GSICS web portal specifications documents
EP09_03 | GSICS user information request form | GDWG | implement a systematic request for user contact information on the GSICS web sites | Web-based request for information form
EP07_06 | GSICS Users' Workshop | GDWG+GRWG | Support GSICS by interacting and getting input from User community | Meeting report
EP09_04 | Resolution of GSICS Users' Workshop Action/Recommendation Items | GDWG+GRWG | Review the recommendations from GSICS Users Workshop(s) and address them as appropriate. | Resolution, and/or plan for resolution, of actions/recommendations
GDWG04_02 | User feedback regarding NetCDF versions | EUMETSAT | Solicit users’ preferences on NetCDF versions and report at Users’ Workshop | Report
EP06_14 | End-to-end demonstration | EP, GCC, GDWG, GRWG | establish an end-to-end demonstration toward an operational GSICS by including beta-users in the GSICS process | Report from the beta users
GRWG05_18 | GHRSST contact information | EP and RAL | Dave Smith to provide Exec Panel with contact at GHISST | Contact
GIP 1.3 | Report to CEOS plenary | WMO | Inform CEOS and coordinate (as part of WMO report) | Briefing and debriefing
GIP 1.3 | Report to CGMS | WMO, EP | Inform CGMS and coordinate with their activities | Briefing and debriefing
EP09_05 | Discuss adapting EUMETSAT/GSICS fact sheet to create a “GSICS fact sheet" | WMO+EUMETSAT | WMO to discuss with EUMETSAT the possibility of adapting the EUMETSAT/GSICS fact sheet to create a “GSICS fact sheet, taking due account of EUMETSAT copyright. | Brief and debrief
EP09_06 | Ensure user accessibility to consistent instrument SRFs | GCC+WGCV | Investigate the consistency of sensor SRF information among the GCC and the WGCV websites and inform WGCV with a view to establish web links if appropriate. | Web links to consistent SRFs
| Expanding Membership and Partnership |  | Involve all agencies with relevant earth operation programs and strengthen links with partner initiatives
EP09_07 | Invitation for USGS report | GRWG | Invite USGS to report on relevance of GSICS for terrestrial applications of Landsat data at GRWG. | Invitation
EP09_08 | Invite IMD to join GSICS | WMO | Send a letter to the Director General of IMD inviting IMD to join GSICS | Letter mailed to IMD
EP09_09 | Invite ESA (NASA) to present DMITRI (MODIS calibration) at GRWG | GRWG | Invite Marc Bouvet (ESA/ESTEC) and Jack Xiong (NASA/GSFC) to present DMITRI (Database for Imaging Multi-spectral Instruments and Tools for Radiometric Intercomparison) and MODIS calibration at GRWG | Invitation
EP09_10 | Invite to SCOPE-CM to issue a Needs Statement | EP | Invite SCOPE-CM to issue a Statement of Needs describing the deliverables expected from GSICS | Invitation
EP06_05 | GRUAN | GRWG | GRWG to consider the possible recommendations to GRUAN regarding coordinated radio-sondes and satellite observations (report to AOPC expected from NOAA/ Tony Reale) and report to Executive Panel members. | Recommendations list
EP07_08 | ISCCP | EP Chair | M. Goldberg to work with ISCCP to define the specifications of GSICS products, based on GSICS correction, to be used in ISCCP for comparative evaluation with the current ISCCP inter-calibration schemes, and to define practical modalities for such a test. | Requirements definition statement
EP08_03 | JAXA |  | JAXA to present an overview on its calibration activities and plans at an Executive Panel session.
EP08_04 | JAXA+CNES | JAXA+CNES | JAXA and CNES to report at EP-10 on GOSAT-IASI inter-calibration. | Report
EP08_14 | ISRO | ISRO | ISRO, JAXA to consider nominating points of contacts for GRWG and GDWG in advance of the next sessions of these working groups. (Completed for JAXA) | POCs
| Consolidating Infrastructure and Operational Practices |  | Specify, organize, archive and disseminate GSICS data and information
EP09_02 | Propose plan for development of joint procedures between GSICS and GPM X-Cal. | EP | M. Goldberg will correspond with A. Hou (NASA) and propose a way forward for developing joint procedures among GSICS and GPM X-Cal when relevant. | Briefing and debriefing
GDWG04_11 | GSICS Action Tracking | NOAA and EUMETSAT | NOAA and EUMETSAT to create an evaluation matrix for documentation and action tracking tools and report back at the next GSICS joint meeting. | Excel tracking tool
GDWG04_12 | GSICS Help Desk | GDWG | Discuss setup of helpdesk functionality | Meeting report
EP07_04 | Product Acceptance Procedure implementation | EP, GCC, GDWG, GPRCs, and GRWG | Introduce potential GSICS Products into the GSICS Procedure for Product Acceptance | Potential products in Demo and/or Pre-operational Modes
GDWG04_14 | GSICS Product Quality Indicators | NOAA | Review the Quality Indicators following the CEOS Cal/Val WG guidelines. | Briefing
GDWG04_06 | GSICS Collaboration Server directory structure | EUMETSAT | Update the directory structure document to take into account the new requirements.
GDWG04_05R | Defining long-term GSICS server storage | GDWG and GRWG | Define additional datasets, such as pixel collocations, that may be place for storage on the GSICS servers. | List of data sets
GDWG04_05R | Defining long-term GSICS server storage | GDWG and GRWG | Definition documentation for permanent storage and definition of according meta dataset. | Report and list of data sets
GDWG04_04 | Filenaming convention: Confirm originator codes | CMA GPRC | CMA (BAWX?) to confirm its originator (CCCC) codes in the file naming convention are correct. | E-mail
GDWG04_13 GRWG05_15 | Gathering Instrument Information | All GPRCs | Find out what instrument information is available for instruments and make this available to the GDWG and GRWG. | Report
GRWG05_08 | Investigation into adding GEO data to SADE database | All GPRC's | Investigate the possibility to supply GEO data over desert sites to the SADE database | Report by e-mail
GDWG04_11R | Instrument monitoring website | GCC+ GDWG | Recommendations for instrument performance monitoring website (CGMS 36 Act…WGII) | Recommendations list
EP06_01 | Instrument monitoring website | GRWG | GRWG to define what should be the key factors that need to be displayed in the GSICS Instrument Monitoring web sites. | Key factors list
EP08_02 | Result display harmonization | JMA+GCC | JMA, in consultation with GCC, to develop a prototype of a unified web page to display GSICS GEO-LEO IR results, along the lines of the sketch discussed among GRWG/GDWG. | Prototype of unified web page
EP08_12 | Vocabulary and guide on uncertainty | NIST | NIST (R. Datla) to develop a draft vocabulary, as part of a future guide on uncertainty for GSICS. | Draft vocabulary list
Product Development and Delivery (1)-Current IR
| GEO-LEO IR |  | Bring GEO-LEO IR intercalibration to operatinal status
EP09_01 | ISRO and the GCC to coordinate for the implementation of GEO-to-LEO algorithms by ISRO. | ISRO+GCC | The current GEO-to-LEO algorithms agreed by GSICS are to be ported and implemented by ISRO with appropriate guidance from GCC. | Implementation of software at ISRO
GCC Directive | CMA to submit GEO-to-LEO correction to the GSICS Procedure for Product Acceptance | CMA | CMA to submit their GSICS correction for the FY-2 satellite imagers to the GSICS Procedure for Product Acceptance | FY-2 GSICS Correction in submission phase
GCC Directive | KMA to submit GEO-to-LEO correction to the GSICS Procedure for Product Acceptance | KMA | KMA to submit their GSICS correction for the COMS satellite imagers to the GSICS Procedure for Product Acceptance | COMS GSICS Correction in submission phase
| LEO-LEO IR |  | Bring LEO-LEO IR intercalibration to operational status
GRWG05_13 | LEO-LEO Channel inter-calibration strategy | GRWG | Review and adopt methodology for the LEO-LEO satellite inter-calibration of the IR channels | Plan
GRWG05_09 | LEO-LEO Visible channel calibration on special targets | CNES | Liaise with Dave Smith or RAL to obtain ATSR and MERIS data from the CEOS-EO Cal/Val portal. | Results
Product Development and Delivery (2)-Heritage instruments
Product Development and Delivery (3)-Current VIS
| GEO-LEO VIS Algorithm development/ Implementation |  | Evaluate GEO-LEO Visible Satellite Instrument Calibration
GRWG05_02 | Combining GEO-LEO solar channel calibration methods | NOAA | Investigate how to combine different solar calibration methods. | Report
GRWG05_04-05 | Assessment of calibration error propagation method | GRWG Solar PIs | Review error propagation example and consider how it could apply to their solar channel calibration method. | Web meeting(s)/Report
GRWG05_10 | SEVIRI data transfer | EUMETSAT | Send SEVIRI pristine sea surface data to CNES for analysis. | SEVIRI data transferred to CNES
GRWG05_11 | Moon calibration method review | NOAA | Review existing quantitative assessment of Lunar calibration method produced for CERES. | Report
Product Development and Delivery (4)-Microwave
LEO-LEO MW Algorithm Development/ Implementation
EP03_06 | Absolute MW calibration | GCC | GCC (F. Weng) will prepare a presentation on absolute calibration for MW channels at GRWG-5. | Presentation
| Glossary of Colors | Milestone Status
On Schedule
Unplanned diversions to schedule, but still progressing
Task cannot be completed as proposed
Completed
Note on F18: bobi: An update of the WMO web site was made in 2010. Do we want to re-evaluate the web site in 2011?
Note on F20: bobi: A milestone from Q2 2010. All GPRCs web sites have a Version 1.0, except for KMA. bobi: November 8, 2010 Update - KMA is working on its website towards the end of the year. All the others are good.
Note on F21: GSICS: An action from Q4 2010. The comment provided during that time is: Current web support to create the sophisticated web architecture associated with a central GSICS portal is not available at this time. GSICS: GDWG does not see a need for such a sophisticated web architecture at this time.
Note on I23: bobi: Workshop planned during the EUMETSAT Meteorological Satellite Conference on 5-9 September 2011 in Oslo, Norway.
Note on H26: bobi: This was fulfilled by the September 2010 Users Workshop, but is always relevant to GSICS goals.
Note on F44: GISCS: A Q4 2010 Requirement. November 8, 2010: The current Operations Plan seems adequate.
Note on F45: GSICS: Action from Q4 2010. November 8, 2010 - There does not seem to be a need for this in GSICS in the near term. Other actions items have been given precidence, such as refining file and parameter naming structure.
Note on F47: GSICS: Action due Q4 2010. Not discussed as of yet, as no products within the GSICS Procedure for Product Acceptance have reached the point in the procedure where they are required to develop a Quality Indicator for their products.
Note on F51: GSICS: Action from Q1 2010. GSICS: Aug. 19, 2010 update - Overdue. GSICS: Nov. 8, 2010 update - Nothing from CMA so far. Since they still have no data I see no reason to press them on this.
Note on F52: GSICS: Q1 2010 Action Item. Please see te GCC instrument information kiosk link http://www.star.nesdis.noaa.gov/smcd/GCC/instrumentInfoKiosk.php. Need feedback from the GRWG and Executive Panel regarding its adequacy. GSICS: This will be discussed at the 2011 Joint GRWG/GDWG Meeting. GSICS: The underlying issue is the format for SRFs. Right now it is all over the place, with varying degree of accompanying information. There is an emerging standard for this kind of info: SensorML. It is being adopted by a growing number of international standard organizations. CEOS likes it, too.
Note on F53: GSICS: Action was due Q2 2010. What is the status of this action?
Note on F54: GSICS: Recommendation was suggested to be completed by due Q3 2010. NOAA has created instrument performance monitoring statistics for its operations instruments that can be view on-line. GSICS: May need different timelines. Some GPRC had it for years; some have not even committed. GSICS: To be revisited in a February 2011 GSICS Web Meeting.
Note on F64: GSICS: Currently defined as an ad-hoc process where groups that are doing LEO-LEO cal submit their cal products to GSICS.
Note on F70: GSICS: By the next Joint GDWG-GRWG Meeting in 2011.
Note on F71: GSICS: Report full assessment by the next Joint GDWG-GRWG Meeting in 2011.
Note on F72: GSICS: An action from Q3 2010. GSICS: Still to be worked.
Note on F73: GSICS: Action was due Q4 2010. This should be SeaWIFS and not CERES.

## Original
Task Name | Lead | Description | Deliverable | Q1 | Q2 | Q3 | Q4
Project meeting milestones |  | Governance
Executive Panel Meeting | EP | Provide the GSICS program guidelines | Meeting report |  | ∆ |  | ∆
GRWG/GDWG Joint Meeting | GDWG/GRWG | Resolving related data and science issues | Meeting report | ∆
GRWG Web Meeting | GRWG | Support GSICS by resolving related scientific issues | Meeting report | ∆ | ∆ | ∆ | ∆
GDWG Web Meeting | GDWG | Support GSICS by resolving related data management issues | Meeting report |  | ∆ |  | ∆
Outreach and user interaction |  | Inform GSICS community & beyond and seek feedback
Quarterly Newsletter | GCC | Inform members and stake-holders | Newsletter delivered electronically | ∆ | ∆ | ∆ | ∆
Quarterly Anomaly Reports | All GPRCs | Reports of satellite instrument anomalies | Quarterly Report | ∆ | ∆ | ∆ | ∆
GSICS Information, Services, and Products Roster (GISPR) | EP, GCC | 1. Submit to NWP and climate user groups | Submit to GCOS, RSSC-CM, CEOS WGCV, NWP workshop | ∆
2. Review the feedback received
GSICS Users' Workshop | GDWG-GRWG | Support GSICS by interacting and getting input from User community | Meeting report |  |  | ∆
End-to-end demonstration | GCC, GDWG, GRWG, ExP | establish an end-to-end demonstration toward an operational GSICS by including beta-users in the GSICS process | Report from the beta users |  |  |  | ∆
Report to GCOS/AOPC | EP | Inform GCOS/AOPC and coordinate with their activities | Briefing and debriefing |  | ∆
Report to CEOS Cal/Val | EP | Inform CalVal and coordinate with their activities | Briefing and debriefing |  |  | ∆
Report to CEOS plenary | WMO | Inform CEOS and coordinate (as part of WMO report) | Briefing and debriefing |  |  |  | ∆
Report to CGMS | WMO, EP | Inform CGMS and coordinate with their activities | Briefing and debriefing |  |  |  | ∆
Participate in Conferences/workshops/panels |  | Participate in GRC, SPIE, WCRP/SSC, GCOS/SC, BIPM to raise awareness and get feedback
BAMS article on GSICS | EP | Inform satellite and user community about GSICS | Draft paper |  |  | ∆
WIGOS Pilot Project | GCC, WMO | To develop WIGOS Pilot Project proposal based on GSICS activities (CGMS 36 Action…) |  | ∆
Data Management and other cross-cutting tasks |  | Specify, organize, archive and disseminate GSICS data and information
GSICS Web Sites | GCC, All GPRCs | Provide information, reports, results and links to Members | GSICS web site | ∆ | ∆ | ∆ | ∆
File and Parameter Naming Conventions | GDWG | Adopt and amend an established file and parameter naming conventions appropriate for GSICS data sets. | GSICS File and Parameter Naming Systems | ∆
GSICS Collaborative Server | EUMETSAT, NOAA | Collaborative Servers up and running with THREDDS/OPeNDAP software and common directory structure | On-line functional collaborative data servers |  | ∆
GEO-LEO IR imager channel updates to collaborative server and web | All GPRCs | Post GEO-LEO IR imager channel updates to collaborative server and web | Available data sets, plots, and tables of results | ∆ | ∆ | ∆ | ∆
GSICS Twiki | All | Begin to create collaborative GSICS documentation using TWiki software running on NOAA server | LEO-LEO and GEO-LEO documentation 80 % complete | ∆ | ∆ | ∆ | ∆
Documentation | GDWG | Initial archiving of documentation and codes | Description and initial archiving |  |  | ∆
Result template | GRWG-GDWG | Improve and harmonize presentation of results in graphs and tables | Templates |  | ∆
Service Specification | GCC + GPRCs | Detail the specification of products and make it available through a portal | Detailed product descriptions |  |  |  | ∆
Product Acceptance Procedure implementation | GCC+ GRWG +GDWG | Establish scientific and data management criteria to be met by GSICS products | Criteria |  |  |  | ∆
SADE data request mechanism | GRWG-GDRG-CNES | Adopt a mechanism for SADE data requests from GSICS partners, implement by CNES | Interface implemented | ∆
Additions to SADE targets | GRWG-CNES | Propose / evaluate new targets sites for inclusion into SADE, to be discussed at CNES at joint GRWG-GDWG+C24 | Selected targets | ∆
Instrument monitoring website | GCC+ GDWG | Recommendations for instrument performance monitoring website (CGMS 36 Act…WGII)
Instrument characteristics repository | GCC + GPRCs | To make available the instrument characterization of their imaging and sounding instruments in polar and geostationary orbit, in particular the spectral response functions, through a link from the GCC website (CGMS 36 Act…WGII) | Links to detailed characteristics |  |  |  | ∆
Pre-launch actions | NIST + GCC, ExP | Pre-launch instrument characterization guidelines(See action 5.3) Action to be conducted in cooperation with CEOS WGCV | Guidelines
Instrument calibration | GRWG | Develop a procedure to calculate the best estimate of a calibration of a particular instrument channel at a given point in time | Procedure
LEO-LEO UV, Visible, IR and MW Intercomparison |  | Evaluate LEO Satellite Instrument Calibration
LEO-LEO operational updates | NOAA/CMA | Add new LEO satellite instruments (NOAA-N', FY-3), create and implement NetCDF output modules, and expand documentation | New data for evaluation, output and filename structures aligned with GSICS standards, completed documentation |  |  |  | ∆
LEO-LEO microwave imager inter-comparison | NOAA | Perform baseline inter-sensor calibration for microwave imagers (SSM/I, SSM/IS, TMI, WindSat, AMSR-E, etc.) | Evaluation report |  |  | ∆
LEO-LEO GOME-2 and OMI data inter-comparison | NOAA | Establish and implement software for LEO-LEO GOME2 and OMI data inter-comparison | Evaluation report |  |  | ∆
LEO-LEO Analysis | NOAA | Routinely evaluate measurement comparability (AMSU, SSM/I, HIRS, AVHRR, MODIS, AIRS) | Evaluation report | ∆ | ∆ | ∆ | ∆
Regular AIRS-IASI comparison | CNES / NOAA | Routinely evaluate measurement comparability (IASI, AIRS) through several methods | Report | ∆ |  | ∆
LEO-LEO historical analysis | NOAA | Perform SNO analysis for historical operational AVHRR, AMSU-A, MSU, HIRS, etc. | Pending External Funding | ∆ | ∆ | ∆ | ∆
LEO-LEO product acceptance within GSICS | GCC, GRWG, GDWG, EP | Put LEO-LEO product through GSICS Procedure for Product Acceptance | GSICS EP Approval of LEO-LEO Product |  |  |  | ∆
Further developments (LEO-LEO)
LEO-LEO Visible channel calibration on special targets | CNES | Using SADE database, intercalibration of MODIS, MERIS, SPOT/VGT, Parasol, plus extension to AVHRR data from the long term data range processing | Results
GEO-LEO Algorithm development/ Implementation |  | Evaluate GEO and LEO Satellite Instrument Calibration
GEO-LEO Inter-Calibration for IR channels | All geo-GPRCs | Routine inter-calibration of respective GEO with AIRS and IASI | Periodic delivery of results to GCC |  |  | ∆
GEO-LEO Inter-Calibration for IR channels | GCC | Establish baseline inter-calibration of all GEOs with AIRS and IASI | Baseline comparison as needed |  |  | ∆
Algorithm Comparison | GCC | Compare algorithms and their results at GPRCs, focusing on IR for 2009 | Report of differences and suggestions of improvements |  |  |  | ∆
Further developments
AIRS/IASI Inter-Calibration using geostationaries as Transfer Radiometer | NOAA, EUMETSAT, KMA, JMA | Evaluate the AIRS/IASI difference with "double differencing" of (GOES-AIRS) - (GOES-IASI) | Evaluation report |  | ∆
GEO Midnight Calibration Anomaly | JMA/NOAA | Use GSICS LEO-GEO inter-calibration to assess the status (MTSAT) and correction (GOES) of the midnight calibration anomaly | Evaluation report |  |  | ∆
GOES-13 Imager 13.3 um Channel SRF correction | NOAA | Use GSICS LEO-GEO inter-calibration to quantify and correct errors in GOES-13 Imager 13.3 um channel SRF | Implementation to NOAA Satellite operation | ∆
RTM Bias Characterization | NOAA | RTM bias characterization for select GEO and LEO IR and microwave instrument window channels, and possibly IR water vapor channels for selected clear atmospheric conditions | Evaluation results |  |  | ∆
GEO and LEO Solar Channel Inter-Calibration | All geo-GPRCs | Demonstrate a baseline algorithm | Initial results and evaluation |  |  |  | ∆