## Sheet1
Action Id | Item | Effort Level | Urgency | Summary | Lead | What to Do | Expected Completion | Actual Completion | Deliverable Usage
GDWG_2015.4a1 | Review Websites | L | H | ISRO to provide GPRC web pages to GDWG co-chairs for review by 30/04/2015. | ISRO | Configuration | 2015-04-30 | 2016-03-02 |  | Pradeep informed Tim and Masaya of the URL during the 2016 annual meeting.
GDWG_2015.4a2 |  | M | H | EUMETSAT to support the review of all GPRC for minimum content and provide suggestions for updates. | EUM | Analysis | 2015-06-30 | 2016-02-16 |  | Informed at the 2016 annual meeting
GDWG_2015.4a3 |  | M | M | ISRO to support GCC to provide a satellites constellation image for the GCC website. | ISRO | Tech Support | Confirm by Email
GDWG_2015.4a4 |  | L | M | WMO to update JMA GPRC website URL on the WMO portal. | WMO | Configuration | 2015-03-31 | 2015-03-24
GDWG_2015.4a5 |  | L | M | KMA to add hyperlinks to the GCC, product catalogue, and THREDDS servers. | KMA | Configuration | 2015-04-30 | 2015-04-30
GDWG_2015.4a6 |  | L | M | KMA to modify a hyperlink to CMA GPRC website. | KMA | Configuration | 2015-03-31 | 2015-03-31
GDWG_2015.4a7 |  | L | M | WMO to contact current ISRO EP member to provide updates to their GSICS members. | WMO | Information | 2015-03-31 | 2015-03-25
GDWG_2015.4b | Review Standards | M | M | IMD are kindly requested to provide ISRO LocationIndicator and sub centre indicator for updating the Manual on Codes document (common codes Table C-12, note CCCC code is DEMS) prior to the development of their productions identified by a WMO filename where this information is required. Note, some time is needed to publish such updates. | IMD | Information | 2015-04-30
GDWG_2015.4c1 | Existiing NetCDF format Updates | H | H | The GRWG need to examine the aspects to be revalidated and confirm they have no major impact. (ref: changing the existing GEOLEOIR variables to combined versions). | EUM/JMA | Analysis | 2015-05-31 | 2016-02-16
GDWG_2015.4c2 |  | M | M | Update the GEOLEOIR GSICS product template on the Wiki. | JMA | Configuration | 2015-07-31 | 2015-09-16 | Developers | Pete has provided a XSD for this
GDWG_2015.4c3 |  | M | L | Update the Wiki to include the accurate timing information as an optional comment attribute of the validity_period in their products. | JMA | Information | 2015-07-31 | 2016-03-02 |  | To be discussed in 2016 GDWG session
GDWG_2015.4c4 |  | M | H | JMA to provide list of new GEOLEOIR global attributes to GDWG members and member should provide input within 1 week on the proposed updates | JMA | Information | 2015-05-31 | 2015-09-16 |  | Discussed in 2016 GDWG session and a new action GDWG.2016.6g.2 was assigned to JMA.
GDWG_2015.4d | New GSICS Products | H | H | identify if using the enhanced data model has impact to the usage of the new products. | EUM/JMA | Analysis | 2015-07-31 | 2016-03-03 |  | Discussed in 2016 GDWG session and a new action GDWG.2016.5b.1 was assigned to JMA.
GDWG_2015.4e | Data Version Updates | M | H | GCC to support the revising of the GSICS versioning and update the Wiki. | GCC | Information | 2015-06-30 | 2016-02-16
GDWG_2015.4f | Proposed MW Standards | H | H | NOAA to provide templates of proposed WMO file name and the content of the MW GSICS product on the GSICS wiki | NOAA | Analysis | 2015-06-30 |  |  | Could be done in 2016
GDWG_2015.4h1 | Repository for Code | L | H | all GPRC to report what version controlling software is used and propose possible software to be used in the GSICS activities. | KMA | Information | 2015-04-30 | 2015-04-30
GDWG_2015.4h2 |  | L | H | GCC to check the availability to provide administration role on gitHub. | GCC | Analysis | 2015-06-30 |  | GDWG
GDWG_2015.4i | Existing tools updates | H | H | EUMETSAT to provide estimate the resources needed and the expectations for when the updates will be implemented, and present these to the GDWG and EP to request for resources. | EUM | Analysis | 2015-05-31 | 2015-05-18
GDWG_2015.4j | Product Content Access Study | M | H | CMA to discuss with CMA GPRC members on the usefulness of GSICS products in database. | CMA | Analysis | 2015-12-31 | 2016-01-20 |  | CMA GRWG does not need this kind of products at present
GDWG_2015.4l1 | Event log | M | H | IMD and ISRO to nominate a representative that is part of the calibration events task team (CGMS-42: WGII/3 Action 42.02). | IMD/ISRO | Information | 2015-04-30
GDWG_2015.4l2 |  | M | M | EUMETSAT and JMA to provide templates of landing page to GDWG (or GSICS wiki). | EUM/JMA | Specification | 2015-04-30 | 2015-12-16 | Users
GDWG_2015.4l3 |  | H | M | EUMETSAT to write a white paper on the standard nomenclature for calibration logging and monitoring. | EUM | Analysis | To be confirmed by Email |  |  | In progress
GDWG_2015.6a1 | Clarification of storage of GSICS support data | M | H | JMA GRWG to provide the list of existing SRF data sets to be stored. GPRC responsible for these data sets shall provide them to GDWG co-chair as soon as possible. | JMA | Information | 2015-07-31 |  |  | delayed
GDWG_2015.6a2 |  | M | H | JMA to provide the netCDF template to GDWG co-chair for these SRF files. | JMA | Specification | 2015-04-30 | 2015-04-29 | Developers
GDWG_2015.6a3 |  | H | H | EUMETSAT to support the generation of the existing SRF files into the netCDF format. | EUM | Implementation | 2015-12-31
GDWG_2015.6a4 |  | M | H | GCC to update the Instrument Info Kiosk with the SRF netCDF files provided by EUMETSAT. | GCC | Configuration | 2015-12-31 | 2016-02-16 | Users
GDWG_2015.6a5 |  | L | H | The GEOLEOVISNIR or LEOLEOVISNIR shall include an optional global attribute referencing the location of the associated SRF netCDF file. | EUM/JMA | Specification | 2016-03-01 | 2016-03-03 |  | Discussed in 2016 GDWG session
GDWG_2015.6a6 |  | L | H | EUMETSAT to investigate how THREDDS can be used to limit access to these data sets. | EUM | Information | 2015-06-30 | 2015-04-29 |  | No way to limit the access on THREDDS. This was informed at the 2016 annual meeting
GDWG_2015.6b1 | Tool for GRWG | H | H | GDWG co-chair to support GRWG to implement the recommendations for sharing work in a Data Managed way. | EUM/JMA | Tech Support | 2015-04-30 |  | Users | In progress
GDWG_2015.6b2 |  | H | H | EUMETSAT to provide requirements and design for the netCDF GSICS product checker. | EUM | Specification | 2015-06-30 | 2016-02-16 |  | Discussed in 2016 GDWG session
GDWG_2015.6b3 |  | H | H | CMA, IMD, JMA and KMA to collaborate in the implementation of the netCDF GSICS product checker. | JMA/KMA/CMA/IMD | Implementation | 2015-12-31 |  | GDWG | delayed
GDWG_2015.6c1 | Directory Structure | L | H | CMA to check the proposed new THREDDS server's directory structure with their GRWG member if the new structure fits the needs of CMA. | CMA | Analysis | 2015-04-30 | 2015-04-30
GDWG_2015.6c2 |  | H | M | EUMETSAT to take the lead in performing these updates and provide these to the administrators of the other collaboration servers. | EUM | Configuration | 2015-05-31 | 2016-02-16 | GDWG | Discussed in 2016 GDWG session
GDWG_2015.6d1 | Collaboration server mirroring of products | M | H | CMA to investigate if their GSICS source data download tool can be used to perform the transfer of GSICS products between the collaboration servers support the mirroring of the products can be achieved. | CMA | Analysis | 2015-05-31 | 2016-02-16 | Uses | A way to get GSICS products on EUM/NOAA THREDDS was presented at the 2016 annual meeting.
GDWG_2015.6d2 |  | M | M | NOAA to investigate the mirroring of EUMETSAT products on the NOAA server. | NOAA | Implementation | 2015-12-31 | 2016-02-16 | Users | A way to get GSICS products on EUM/CMA THREDDS was presented at the 2016 annual meeting.
GDWG_2015_6f | Document Management System | M | M | WMO and GPRCs to provide the GCC with examples of document management procedures including templates to support the creation of GSICS branding documentation templates. | GCC | Information | 2015-12-31 | 2016-02-16 | GSICS WG
GDWG_2015.8a | Summary of Tasks | L | M | EUMETSAT to provide a harmonised action identifier for the working groups and the EP. | EUM | Specification | 2015-05-31 | 2016-02-16
GDWG_2015.9b1 |  |  |  | Sebastien Wagner (GRWG) needs to iterate with Peter Miu on what to put in place to share the GIRO code and the GLOD (GSICS Lunar Observation Dataset). | EUM | Specification | 2015-05-31 | 2015-05-31
GDWG_2015.9b2 |  |  |  | GDWG will come with a proposal on how to number the actions. The action tracking tool should include the actions coming from the web meetings. | EUM/JMA | Information | 2015-05-31 | 2016-03-01 | GDWG | Closed in 2016 annual meeting plenary - accepted by group
GDWG_2015.9b3 |  |  |  | Alternatives to the current action tracking tool should be discussed at further stage (web meeting). | EUM/JMA | Specification | 2015-05-31 | 2016-03-03 |  | Discussed in 2016 GDWG session
Note on J8: Jerome's comment on 2015-05-04: Action was completed by WMO on 25 March (see attached). There was no formal
Note on J11: discussion at gsics-dev
Note on I13: 2015-04-30 was extended due to a delay of Masaya's action
Note on I19: 2015-04-30 was extended to discuss at the EP-16 (2015-04-30 email from Peter)
Note on I20: 2015-4-30 was extended (2015-04-30 email from Thomas)
Note on I35: due date was set to 31 May (2015/04/30 email from Thomas)