## Slide 1: GRWG Summary Decisions, Actions, Recommendations

## Slide 2: Mini Conference
CLARREO Pathfinder inter-calibration in reflected solar: project status (Constantine Lukashin)
CLARREO IR Sensor, Calibration Accuracy and Traceability (Joe Taylor)
CLARREO IR Intercalibration (Dave Tobin)
GRUAN and GSICS (Tony Reale)
Current Status and Lessons from TRMM/GPM XCAL Calibration Activities (Wesley Berg)
Intercal activities and products within the Atmospheres SIPs (Bob Holz)
Update on PATMOS-X products (Andy Heidinger)

## Slide 3: Mini Conference
GWG.2017.1e.1 | GRWG to coordinate with B. Wielicki + Exec panel the writing of a white paper to support the CLARREO project |  | 
GWG.2017.1j.1 | Andy to discuss with GCC how to promote the PATMOS-x products through the GPPA |  | 

## Slide 4: Plenary(GPRC report)-1/3
GWG.2017.2b.1 (R) | GCC to check with NOAA the status of the IR code . GCC to follow up with IMD |  | 
GWG.2017.2b.2 | GRWG_15.39 + GRWG_15.55 to be closed (with the provided statements) | Fred Wu | 
GWG.2017.2c.1 | CNES to report on progress with analysis of IASI moon observations at LCW |  | 
GWG.2017.2c.2 | GCC to interact with EUMETSAT for IASI readers. |  | 
GWG.2017.2d.1 (R) | CMA and CNES to provide more info on opportunities for inter-calibration with their respective CO2 band instruments (Microcarb and Tansat) |  | 

## Slide 5
GRWG_15.39 | NOAA to update the product user guide for GOES-IASI products to inform about the range of diurnal applicability | Fred Wu | 29 Feb 2016 | Late
GRWG_15.55 | NOAA to investigate inter-channel calibration with IASI. | Fred Wu | 29 Feb 2016 | Late

## Slide 6: Plenary(GPRC report)-2/3
Decision | It is agreed that corrections based on comparisons purely in geophysical parameter spaces shall not be called a GSICS calibration correction. |  | JAXA agency report
GWG.2017.2g.1 (R) | GSICS shall provide recommendations on the naming of the corrections to separate calibration correction from system correction, following the results of the discussion raised by Bertrand and agreed. |  | JAXA agency report

## Slide 7: Plenary(GPRC report)-3/3
GWG.2017.2h.1 (R) | EUMETSAT and IMD to interact for comparisons between Meteosat-8 and INSAT-3D/3DR. |  | 
GWG.2017.2i.1 | EUMETSAT (P. Miu) to provide info to ISRO regarding the access to IASI data. |  | 
GWG.2017.2i.2 | EUMETSAT (P. Miu) to investigate hosting ISRO GSICS products on the EUMETSAT GSICS collaboration server |  | 
GWG.2017.2i.3 | NASA to support IMD with MODIS data. - Existing action - no new one needed? | GVNIR.2016.2n.1 (ISRO) | 
GWG.2017.2j.1 | GCC and KMA to check the status of KMA’s products in the GPPA |  | 
GWG.2017.2k.1 | EUM to provide the degradation model for GOME-2 to NASA (Dave Doelling). |  | 

## Slide 8: Plenary (WG report/Briefing)-1/2
GWG.2017.3a.1 | CMA(Scott) to confirm whether CMA can register for the new messaging service from China |  | 
GWG.2017.3a.2 | GCC to organise a web meeting before the User’s workshop |  | 
GWG.2017.3a.3 | Each agency should indicate who should represent the users on their side. Manik to coordinate. | GSICS User’s workshop | 
GWG.2017.3c.1 | GRWG Chair to check with EP if the ToR could be changed to address GRWG_15.1 | GSICS_15.1 G.2 A43.16 | 
GWG.2017.3o.1 | Rob (EUMETSAT) to report back at the next annual meeting on the investigation to do an homogenisation in the radiance space (instead of in the spectral space with the SRFs) |  | 

## Slide 9
GSICS_15.1 G.2 A43.16 | GSICS to work with CEOS/WGCV to: Describe the processes to be followed to ensure consistent calibration meeting climate requirements Describe the required infrastructure (space-based and surface-based) supporting these processes Review the analysis of calibration-related tasks in the logical analysis of the Architecture (with a view to provide a joint input to the Architecture for Climate Monitoring from Space) and report to CGMS-44 | Tim Hewison, Ken Holmlund Dohyeong Kim | 29 Feb 2016 | pending

## Slide 10: Plenary (WG report/Briefing)-2/2
GWG.2017.3m.1 (R) | Recommendation from Data Management (Pete M.) - decisions taken on combining/including corrections within level 1 files should a) make use of the data easier for users and b) reduce maintenance activities as far as possible |  | 
GWG.2017.3n.1 (D) | NWP+RTM approach will not be pursued within GSICS at this time. Instrument operators are encouraged to work together with NWP centres to understand their biases, but there remain many obstacles to achieving absolute agreement between NWP/RTM double differences with other inter-calibration methods due to incomplete cancellation of model biases - especially for window channels |  | 

## Slide 11: GRWG (UV-sub group)
GRWG.2017.4c.1 | Rose to investigate what tasks and tools are needed to pursue the work presented by Larry in the broader context of the UV Subgroup and in particular to identify resources needed with the aim of bringing this to the attention of the EP |  | 

## Slide 12: GRWG (MW-sub group)-1/2
GMW.2017.6a.1 (R) | Get an update from Martin in approx. 6 months. | Lunar calibration
GMW.2017.6b.1 | Ed Kim (NASA) to give an update on the status after launch | JPSS-1 ATMS
GMW.2017.6c.1 | Karsten Fennig to determine feasibility of extracting the inter-calibration algorithms and coefficients from the FCDR and making them a GSICS product | MW Imager FCDR
GMW.2017.6d.1 | Cheng-Zhi Zou to determine feasibility of extracting the inter-calibration algorithms and coefficients from the FCDR and making them a GSICS product | MW Sounder (Oxygen) FCDR
GMW.2017.6e.1 (R) | Get an update from Derek in approx. 6 months | MW reference

## Slide 13: GRWG (MW-sub group)-2/2
GMW.2017.6f.2 | MW Subgroup chair to develop candidate satellite/sensor (inventory) as in orbit references for specific channels (based on some predetermine set of parameters that Manik has outlined...) and note pros and cons, other attributes (publications, etc.)? | In orbit reference session
GMW.2017.6f.2 | Tony Reale (NOAA) to provide a draft uncertainty analysis describing the comparison of example (microwave) instruments to GRUAN sondes - | In orbit reference session
GMW.2017.6g.1 | MW co-chair to develop set of specific tasks to be performed by the Subgroup to intercompare RTM output over static references and surface models. Tasks to be identified within 6 months (Sep. 2017) | RTM issue session

## Slide 14: GRWG (IR-sub group)-1/3
GRWG.2017.7d.1 | Larry to check the status of the GOES sounder product (demo?) | 
GRWG.7bd.1 (R) | CMA (Na Xu) to prepare a report on the current work and to share it with the GRWG for feedback | 
GRWG.2017.7c.1 | JMA to report at the next annual meeting on their investigations regarding the jump observed for the 6.2 micron band | GEO-GEO comparison
GRWG.2017.7c.2 | CMA is encouraged to investigate GEO-GEO comparison. In particular because FY-2 is spinning and therefore is not impacted by midnight anomaly. This exercise would help correcting for the SL issues. | 
GRWG.2017.c.3 | JMA to report at the next annual meeting on their uncertainty analysis in the gap filling method with AHI/AIRS. | 

## Slide 15: GRWG (IR-sub group)-2/3
GRWG.2017.c.4 (R) | JMA to report at the next annual meeting on the double differences on the bias time series | 
GRWG.7cb.1 | Aisheng (NASA) to get in touch with Chris Moeller to investigate the possibility to have a SRF shift and report back at the later stage (for both VIIRS and MODIS) | 
GRWG.2017.7cb.2 (R) | For MERSI-2, CMA is encouraged to perform similar analysis | MODIS/VIIRS SRF shift
GIR.2017.7d.1 | Tony Reale (NOAA) to provide a draft uncertainty analysis describing the comparison of example (IR) instruments to GRUAN sondes by the next annual meeting | 

## Slide 16: GRWG (IR-sub group)-3/3
GIR.2017.7d.2 | Steve Broberg (JPL) to provide the theoretical uncertainties on the temperatures reported in slide 10 be split according to the scene temperature and the channels and consider updating the analysis accordingly | AIRS analysis ongoing activities
GIR.2017.7f.1 | CMA to review the input needed for the error budget and request those information to the vendor | 
GIR.2017.7f.2 | Fred to explore the feasibility of retrieving SRFs using the method initiated by Manik and report back at later stage (web meeting?) | 
GIR.2017.7a.1 (R) | CMA is encouraged to analyse the results under different conditions to understand the level of WV contamination on the SRFs. the level of contamination by comparing results in different conditions, and recommend the nominal SRFs accordingly. | 

## Slide 17: GRWG (VI/NIR-sub group)
GVNIR.2017.8c.1 (R) | IMD to contact USGS and EUMETSAT for support in processing INSAT-3D Moon images. IMD to attend 2017 Lunar Calibration Workshop | 
GVNIR.2017.8f.1 | Seb to contact ICWG via Andy to evaluate re-calibrated MSG reflectance data. | 
GVNIR.2017.8h.1 | NOAA(Fred Wu) to solicit lunar images from the lunar calibration community to test evaluation of MTF | 
GVNIR.2017.8h.2 | Tom (USGS) will inform Arata of some publication | Some???
GVNIR.2017.8ha.1 | EUM(Seb) to arrange web meeting in April to finalise date for lunar calibration workshop | 
GVNIR.2017.8u.1 | NASA(Raj) to provide SBAF for each GEO imager based on VIIRS v2. Target date: 30 May 2017 | 
GVNIR.2017.8u.2 | 2 Web meetings: Implementation of DCC mode method and writing journal paper by early 2018 | Dave

## Slide 18
Thank you