## Slide 1: GRWG Actions

## Slide 2: Actions on GRWG during 2017/18
Action Id | Summary | Lead | Due Date | Status
A.GWG.2017.1e.1 | GRWG to coordinate with B. Wielicki + Exec panel the writing of a white paper to support the CLARREO project | GRWG Chair | 2018-03-21 | closed (CGMS-45)
A.GWG.2017.1j.1 | Andy to discuss with GCC how to promote the PATMOS-x products through the GPPA. | NOAA(Andy) | 2018-03-01 | Open
A.GWG.2017.2c.1 | CNES to report on progress with analysis of IASI moon observations at LCW | CNES(Bert) | 2018-03-01 | Open
A.GCC.2017.2c.2 | GCC to interact with EUMETSAT for IASI readers. |  | 2018-03-01 | Open
A.GWG.2017.2i.1 | EUMETSAT (P. Miu) to provide info to ISRO regarding the access to IASI data. | EUM(Peter) | 2018-03-01 | Open
A.GWG.2017.2i.2 | EUMETSAT (P. Miu) to investigate hosting ISRO GSICS products on the EUMETSAT GSICS collaboration server. | EUM(Peter) | 2018-03-01 | Open
A.GWG.2017.2i.3 | NASA to support IMD with MODIS data. - Existing action - no new one needed? |  | 2018-03-27 | Open
A.GCC.2017.2j.1 | GCC and KMA to check the status of KMA’s products in the GPPA. | NOAA(Manik) and KMA(Hyesook) | 2018-03-01 | Open
A.GWG.2017.2k.1 | EUM to provide the degradation model for GOME-2 to NASA (Dave Doelling). | EUM(Rose) | 2018-03-01 | Open
A.GWG.2017.3a.1 | CMA(Scott) to confirm whether CMA can register for the new messaging service from China. | CMA(Scott) | 2018-03-01 | Open
A.GCC.2017.3a.2 | GCC to organise a web meeting before the User’s workshop. |  | 2018-03-01 | Open
A.GCC.2017.3a.3 | Each agency should indicate who should represent the users on their side. Manik to coordinate. | NOAA(Manik) | 2018-03-01 | Open

## Slide 3: Actions on GRWG during 2017/18
Action Id | Summary | Lead | Due Date | Status
A.GWG.2017.3c.1 | GRWG Chair to check with EP if the ToR could be changed to address GRWG_15.1. | GRWG Chair | 2018-03-01 | Open
A.GWG.2017.3o.1 | Rob (EUMETSAT) to report back at the next annual meeting on the investigation to do an homogenisation in the radiance space (instead of in the spectral space with the SRFs). | EUM(Rob) | 2018-03-01 | Open
A.GRWG.2017.4c.1 | Rose to investigate what tasks and tools are needed to pursue the work presented by Larry in the broader context of the UV Subgroup and in particular to identify resources needed with the aim of bringing this to the attention of the EP. | EUM(Rose) | 2018-03-01 | Open
A.GMW.2017.5g.1 | MW subgroup would contact NOAA GDWG to get support for product creation if needed. | Ralph Ferraro | 2018-03-01 | Open
A.GMW.2017.6b.1 | Provide an update on the status after launch (currently Sept 2017) | Ed Kim | 2017-12-01 | Open
A.GMW.2017.6c.1 | Determine feasibility of extracting the inter-calibration algorithms and coefficients from the FCDR and making them a GSICS product. | Karsten Fennig | 2018-03-01 | Open
A.GMW.2017.6d.1 | Determine feasibility of extracting the inter-calibration algorithms and coefficients from the FCDR and making them a GSICS product. | Cheng-Zhi Zou | 2018-03-01 | Open
A.GMW.2017.6f.1 | MW Subgroup chair to develop candidate satellite/sensor (inventory), perhaps in the form of a graphical aid, as in orbit references for specific channels (based on some predetermined set of parameters that Manik has outlined...) and note pros and cons, other attributes (publications, etc.)? It should include timelines of sensors and overlap periods. | Ralph Ferraro | 2018-03-01 | Open
A.GMW.2017.6f.2 | Tony Reale (NOAA) to provide a draft uncertainty analysis describing the comparison of example (microwave) instruments to GRUAN sondes. | Tony Reale | 2018-03-01 | Open

## Slide 4: Actions on GRWG during 2017/18
Action Id | Summary | Lead | Due Date | Status
A.GMW.2017.6g.1 | MW co-chair to develop set of specific tasks to be performed by the Subgroup to intercompare RTM output over static references and surface models. Tasks to be identified within 6 months (Sep. 2017). | Ralph Ferraro | 2018-08-01 | Open
A.GCC.2017.6b.1 | GCC to update the action tracking page in response to GRWG/GDWG proposal. |  | 2018-03-01 | Open
A.GCC.2017.6c.1 | GCC to survey from the GSICS users (e.g. during the GSICS User’s Workshop), which netCDF models they are using; classic or enhanced. If enhanced, what features they are using in this model; chunking, …? |  | 2018-03-01 | Open
A.GRWG.2017.7c.1 | JMA to report at the next annual meeting on their investigations regarding the diurnal variation in AHI by using GEO-GEO approach. | JMA(Hidehiko) |  | Open
A.GRWG.2017.7c.2 | CMA is encouraged to investigate GEO-GEO comparison. In particular because FY-2 is spinning and therefore is not impacted by midnight anomaly. This exercise would help correcting for the SL issues. | CMA(Xu Na) | 2018-03-01 | Open
A.GRWG.2017.c.3 | JMA to report at the next annual meeting on their uncertainty analysis in the gap filling method with AHI/AIRS. | JMA(Masaya) | 2018-03-01 | Open
A.GRWG.7cb.1 | Aisheng (NASA) to get in touch with Chris Moeller to investigate the possibility to have a SRF shift and report back at the later stage (for both VIIRS and MODIS). | NASA(Aisheng) | 2018-03-01 | Open
A.GRWG.2017.7d.1 | Larry to check the status of the GOES sounder product (demo?) | NOAA(Larry) | 2018-03-01 | Open
A.GIR.2017.7d.1 | Tony Reale (NOAA) to provide a draft uncertainty analysis describing the comparison of example (IR) instruments to GRUAN sondes by the next annual meeting. | NOAA(Tony) | 2018-03-01 | Open

## Slide 5: Actions on GRWG during 2017/18
Action Id | Summary | Lead | Due Date | Status
A.GIR.2017.7d.2 | Steve Broberg (JPL) to provide the theoretical uncertainties on the temperatures reported in slide 10 be split according to the scene temperature and the channels and consider updating the analysis accordingly. | JPL(Steve) | 2018-03-01 | Open
A.GIR.2017.7f.1 | CMA to review the input needed for the error budget and request those information to the vendor. | CMA | 2018-03-01 | Open
A.GIR.2017.7f.2 | Fred Wu (NOAA) to explore the feasibility of retrieving SRFs using the method initiated by Manik Bali and report back. | NOAA(Fred Wu) | 2018-03-01 | Open
A.GVNIR.2017.8f.1 | Seb to contact ICWG via Andy to evaluate re-calibrated MSG reflectance data. | EUM(Seb) | 2018-03-01 | Open
A.GVNIR.2017.8h.1 | NOAA(Fred Wu) to solicit lunar images from the lunar calibration community to test evaluation of MTF. | NOAA(Fred) | 2018-03-01 | Open
A.GVNIR.2017.8h.2 | Tom will inform Arata of some publication. | USGS(Tom) | 2018-03-01 | closed
A.GVNIR.2017.8ha.1 | EUM(Seb) to arrange web meeting in April to finalise date and venue for lunar calibration workshop. | EUM(Seb) | 2018-03-01 | Open
A.GVNIR.2017.8u.1 | NASA(Raj) to provide SBAF for each GEO imager based on VIIRS v2. Target date 30 May 2017. 2 Web meetings Implementation of DCC mode method and writing journal paper by early 2018. | NASA(Raj) | 2018-03-01 | Open
A.GCC.2017.9f.1 | GCC to coordinate provision of GSICS Corrected test data from the 0.6µm and 11µm channels of all available GEO imagers during Dec 2009 to Ken Knapp to assess the impact of the corrections on ISCCP products. |  | 2018-03-01 | Open
A.GCC.2017.9g.1 | GCC to get the names of POC of agencies for pre-launch characterization workshop. In touch with CEOS. |  | 2018-03-01 | Open
A.GCC.2017.9i.1 | GCC to follow up with Andy Heidinger and Tim Hewison on to send a GSICS Rep to ITOVS and Users NWP Meetings, Cloud Working Group CGMS working groups. |  | 2018-03-01 | Open
A.GCC.2017.9k.1 | GCC to coordinate a preparatory web meeting on clarreo and send out invitations to members to attend the webmeeting. |  | 2018-03-01 | Open

## Slide 6: Actions on GSICS-EP-18 (2017)
Action Id | Summary | Lead | Status
EP-18.01 | to prepare specifications and methodologies for CGMS agency development of operational instrument performance monitoring systems | GRWG Chair (Dohy) | open
EP-18.02 | to assess the utilization RO for microwave instrument monitoring purposes | MW-SG (Chair : Ralph) | open
EP-18.03 | to develop an approach for an Annual GSICS report on the State of the Observing System with Respect to Instrument Performance and Intercomparisons with GSICS Reference Instruments (from presentations given at the GRWG meeting) | GRWG+GDWG (Dohy+Masaya) | open
EP-18.04 | to assess the value of GEO-to-GEO intercalibration for GSICS | IR-SG (Chair : Tim) | closed
EP-18.05 | to develop GSICS Service Specification Document | GRWG + GCC | open
EP-18.06 | to nominate PoC for GDWG | EP members | closed
EP-18.07 | to review maturity criteria for product status | EP members | open

## Slide 7
Thank you