## Slide 1: Preparatory Annual Web meeting for 2018 Annual Meeting in Shanghai, China
Larry Flynn and Manik Bali
GSICS Coordination Center, NOAA
NOAA GDWG

## Slide 2: TABLE OF CONTENT
Actions on GCC
Proposed topics for GSICS Coordination Center
Actions on NOAA-GDWG
Proposed topics for NOAA-GDWG
Proposed talks for UV Session

## Slide 3: GCC- Actions Status
Action Id | Summary | Status
A.GCC.2017.2c.2 | GCC to interact with EUMETSAT for IASI readers. | Closed
A.GCC.2017.2j.1 | GCC and KMA to check the status of KMA’s products in the GPPA. | Closed
A.GCC.2017.3a.2 | GCC to organise a web meeting before the User’s workshop. | Closed
A.GCC.2017.3a.3 | Each agency should indicate who should represent the users on their side. Manik to coordinate. | Closed
A.GCC.2017.6b.1 | GCC to update the action tracking page in response to GRWG/GDWG proposal. | Closed
A.GCC.2017.6c.1 | GCC to survey from the GSICS users (e.g. during the GSICS User’s Workshop), which netCDF models they are using; classic or enhanced. If enhanced, what features they are using in this model; chunking, …? | Open
A.GCC.2017.9f.1 | GCC to coordinate provision of GSICS Corrected test data from the 0.6µm and 11µm channels of all available GEO imagers during Dec 2009 to Ken Knapp to assess the impact of the corrections on ISCCP products. | Data Sets provided to Ken Knapp-
A.GCC.2017.9g.1 | GCC to get the names of POC of agencies for pre-launch characterization workshop. In touch with CEOS. | Mail sent
A.GCC.2017.9i.1 | GCC to follow up with Andy Heidinger and Tim Hewison on to send a GSICS Rep to ITOVS and Users NWP Meetings, Cloud Working Group CGMS working groups. | Open
A.GCC.2017.9k.1 | GCC to coordinate a preparatory web meeting on clarreo and send out invitations to members to attend the webmeeting. | Open
R.GCC.2017.2b.1 | GCC to check with NOAA the status of the IR code . GCC to follow up with IMD. | Closed. No request from IMD received

## Slide 4: Topics-GSICS Coordination Center
GCC – Report – Larry Flynn
Updates on new products and their review status
New Action Tracker
  Updates on Action Tracker
Newsletter-Towards collaboration with contemporary journals
  Membership
  Upcoming Special Issues
GUW 2018 Discussion / Announcement
Welcome to Suggest topics for GCC

## Slide 5
Topics-NOAA-GDWG
Mirroring GSICS Product
New Action Tracker-> Action Tracking on Cloud
  Updates on Action Tracker
Product Monitoring Tool (A.GDWG.20171108.1)
Updates on GSICS Wiki/THREDDS
Welcome to Suggest topics for NOAA-GDWG

## Slide 6: Some Proposed Talks for UV Subgroup
Guanyu Lin from Shurong Wang's, "The technology of a new generation Utraviolet Hyperspectral for detecing global ozone profie"
Houmao Wang, Yongmei Wang, “The successor of Total Ozone Unit (TOU)”
Professor Weihe Wang, "In-orbit calibration for FY-3C/TOU"
Larry Flynn, “Report on the NOAA-20 OMPS”
Larry Flynn, “Update on Three GSICS UV Projects (Solar, reflectivity, Residuals)”

## Slide 7
Thank you