## Sheet1
Reference | Action Description | Actionee | Due date
A.GEP.20180601.1 | EP chair to recommend the nomination of GRWG membership from CNES | EP Chair | EP-20
A.KMA.20180601.2 | KMA to provide the inter-calibration comparison results of COMS/MI using before and after reprocessed CrIS data | KMA | EP-20
A.GRWG.20180601.3 | GRWG to develop a strategy, including the procedure and criteria, on how to handle the long-term drifts of individual instruments identified based on the analyses using GSICS approved approaches. This applies primarily to the VIS/NIR instruments. | GRWG Chair | EP-20
A.GCC&ISRO.20180601.4 | GCC to develop harmonized interface for the instrument performance monitoring website as a baseline for inquiring instrument status. Demo by ISRO | GCC/ISRO | EP-20
A.GRWG.20180601.5 | GRWG to develop monitoring webpage to demonstrate instrument performance recalibrated after applying the GSICS correction | GRWG | EP-20
A.GEP.20180601.6 | EP Chair to request ESA to become full member of GSICS | EP | EP-20
A.WMO.20180601.7-1 | WMO to provide information on WMO cloud to NOAA-GDWG. Information sough includes (ability to upload GSICS products onto the WMO Cloud by members, ability to download data, disk space available and redundancy) | WMO | 2018-08-01
A.NOAA&GDWG.20180601.7-2 | Following above action, NOAA-GDWG to provide information on Clouds available at NOAA and whether they can be used to host GSICS data from member agencies | NOAA-GDWG | 2018-12-01
A.GCC.20180601.8 | GCC to contact GRUAN POC in GSICS ( Tony/Ralph/Cheng-Zhi) to submit yearly updates on 3G (GRUAN-GSICS-GNSS) collaboration to EP | GCC | EP-20
A.ISRO&GCC.20180601.9 | ISRO to contact GCC to obtain knowledge on reading CrIS data to help them inter-calibrate INSAT with CrIS. | ISRO | EP-20
A.GCC.20180601.10 | GCC to simplify and stream line GPPA checklist and share it with members to fast track maturity; Start with KMA and JMA. | GCC | EP-20
A.GCC.20180601.11 | GCC to provide recommendations on new processing and science maturity levels for GSICS products and services | GCC | EP-20
A.GEP&GCC&GRWG&GDWG.20180601.12 | Encourage submission of papers on GSICS in Joint NOAA EUMETSAT Conference to be organized around Oct 2019 in Boston, USA | EP/GCC/GRWG/GDWG | EP-20
A.GCC&GRWG.20180601.13 | GCC/GRWG to develop consensus on contents of intermediate collocation products to be shared with users | GCC/GRWG | EP-20
A.GPRC.20180601.14 | GSICS Agencies to include CrIS in their GEO-LEO monitoring | GPRC | EP-20
A.GEP.20180601.15 | EP to consider how to involve space weather in sub-group | EP | CGMS-46
A.GRWG.20180601.16 | GRWG to review and update the GSICS document “Guide to GSICS Products and Services” to be referred in the WMO document “Guide to the WMO Integrated Global Observing System (Guide to WIGOS)” | GRWG | EP-20
A.GRWG.20180601.17 | GRWG to review and update the WMO CIMO Guide: PART III: SPACE-BASED OBSERVATIONS Chapter 6: Calibration and validation for emphasizing contribution of GSICS to space-based observation | GRWG | 2018-08-01
A.GCC&GRWG.20180601.18 | GCC/GRWG to develop plan for side-events in CGMS Science Working Group meetings | GCC/GRWG | EP-20
R.GCC.20180602.1 | Relax the requirement of User Guide for classical GSICS products | GCC | EP-20
R.GCC.20180602.2 | Relax the requirement of Uncertainty analysis. This can be complimented by Impact Report showing impact of using Cross Calibration and due weighted should be given if Input L1B measurements are taken from Operational data processing streams of host agencies. | GCC | EP-20

## Sheet2
Reference | Action Description | Actionee | Due date
A.GEP.20180601.1 | EP chair to recommend the nomination of GRWG membership from CNES | EP Chair | EP-20
A.GEP.20180601.6 | EP Chair to request ESA to become full member of GSICS | EP | EP-20
A.GEP.20180601.15 | EP to consider how to involve space weather in sub-group | EP | CGMS-46
A.KMA.20180601.2 | KMA to provide the inter-calibration comparison results of COMS/MI using before and after reprocessed CrIS data | KMA | EP-20
A.ISRO&GCC.20180601.9 | ISRO to contact GCC to obtain knowledge on reading CrIS data to help them inter-calibrate INSAT with CrIS. | ISRO | EP-20
A.WMO.20180601.7-1 | WMO to provide information on WMO cloud to NOAA-GDWG. Information sough includes (ability to upload GSICS products onto the WMO Cloud by members, ability to download data, disk space available and redundancy) | WMO | 2018-08-01
A.NOAA&GDWG.20180601.7-2 | Following above action, NOAA-GDWG to provide information on Clouds available at NOAA and whether they can be used to host GSICS data from member agencies | NOAA-GDWG | 2018-12-01
A.GEP&GCC&GRWG&GDWG.20180601.12 | Encourage submission of papers on GSICS in Joint NOAA EUMETSAT Conference to be organized around Oct 2019 in Boston, USA | EP/GCC/GRWG/GDWG | EP-20
A.GPRC.20180601.14 | GSICS Agencies to include CrIS in their GEO-LEO monitoring | GPRC | EP-20
A.GRWG.20180601.3 | GRWG to develop a strategy, including the procedure and criteria, on how to handle the long-term drifts of individual instruments identified based on the analyses using GSICS approved approaches. This applies primarily to the VIS/NIR instruments. | GRWG Chair | EP-20
A.GRWG.20180601.5 | GRWG to develop monitoring webpage to demonstrate instrument performance recalibrated after applying the GSICS correction | GRWG | EP-20
A.GRWG.20180601.16 | GRWG to review and update the GSICS document “Guide to GSICS Products and Services” to be referred in the WMO document “Guide to the WMO Integrated Global Observing System (Guide to WIGOS)” | GRWG | EP-20
A.GRWG.20180601.17 | GRWG to review and update the WMO CIMO Guide: PART III: SPACE-BASED OBSERVATIONS Chapter 6: Calibration and validation for emphasizing contribution of GSICS to space-based observation | GRWG | 2018-08-01
A.GCC&GRWG.20180601.13 | GCC/GRWG to develop consensus on contents of intermediate collocation products to be shared with users | GCC/GRWG | EP-20
A.GCC&GRWG.20180601.18 | GCC/GRWG to develop plan for side-events in CGMS Science Working Group meetings | GCC/GRWG | EP-20
A.GCC.20180601.8 | GCC to contact GRUAN POC in GSICS ( Tony/Ralph/Cheng-Zhi) to submit yearly updates on 3G (GRUAN-GSICS-GNSS) collaboration to EP | GCC | EP-20
A.GCC.20180601.10 | GCC to simplify and stream line GPPA checklist and share it with members to fast track maturity; Start with KMA and JMA. | GCC | EP-20
A.GCC.20180601.11 | GCC to provide recommendations on new processing and science maturity levels for GSICS products and services | GCC | EP-20
A.GCC&ISRO.20180601.4 | GCC to develop harmonized interface for the instrument performance monitoring website as a baseline for inquiring instrument status. Demo by ISRO | GCC/ISRO | EP-20