## Slide 1
Actions
from CGMS-47 and GSICS-EP-20

## Slide 2: Actions from CGMS-47
Actionee | AGN item | Action# | Description | Action feedback/closing document | Deadline | Status | HLPP ref
GSICS | WGII/4 | A47.01 | GSICS to expand GSICS Report on the State of the Observing System to successively cover the calibration status of all instruments relevant GSICS. | 2020 Mar 6; GSICS meeting postponed. 2020 Jan 9 WGII IS #1: To be reviewed by GSICS meeting in March 2020.(M. Goldberg) | CGMS-48 | OPEN | 
IROWG, ICWG, IWWG, IPWG, ITWG, GSICS, WGClim | WGII/5 | A47.15 | The ISWGs, WGClimate and GSICS to review WGIII Risk assessment and consider mitigation opportunities. |  | CGMS-48 | OPEN | 
GSICS, WGClim, SCOPE-CM | WGII/8 | A47.21 | GSICS, WGClimate and SCOPE-CM to organise a workshop on calibration supporting reprocessing. | 2020 Jan 9 WGII IS #1: (First review to take place at GSICS meeting in March 2020, Korea) | Mar 2020, CGMS-48 | OPEN | 
GSICS | WGII/11 | A47.24 | GSICS to review SWCG white-paper on calibration and consider opportunities for GSICS support to aforementioned activity. |  | Mar 2020 | OPEN | 
GSICS | from WGIII | A47.29 | GSICS to continue cross calibration progress of microwave imagers. (WGII) | 2020 Jan 9 WGII IS #1: To be reported at next annual GSICS EP meeting in May 2020 New action requested by WGIII | CGMS-48 | OPEN | 
NOT to discuss the all the actions BUT to remind and suggest who will lead the actions
CGMS Secretariat
To hold the CGMS Working Groups discussions on the planned dates of 25-29 May, using WebEx meetings (including GSICS-EP)
To hold the CGMS Plenary meeting on 25-26 August 2020 in EUMETSAT Headquarters’ in Darmstadt, Germany

## Slide 3: Actions from GSICS-EP-20(1/2)
Reference | Action Description | Actionee | Due date
A.GEP.20190517.1 | EP Chair to coordinate with WIGOS for utilizing GSICS Product Catalog with Quicklooks in WDQM system. | EP Chair | EP-21
A.GEP.20190517.2 | EP Chair to coordinate with WIGOS to enhance collaboration to integrate GSICS into WIGOS. | EP Chair | EP-21
A.GEP.20190517.3 | NASA, ESA, ISRO to provide a landing page with instrument link(s) for inclusion in the satellite instrument pages in WMO-OSCAR. Initially, the landing page will provide a link or link(s) to those satellite instruments of high interest to GSICS. | NASA, ESA, ISRO | EP-21
A.GEP.20190517.4 | EP members to review the CGMS SWCG white paper for a possible contribution to SWCG activity. | EP members | EP-21
A.GEP.20190517.5 | ROSCOSMOS to remove requirement of login on their GPRC page. | ROSCOSMOS | EP-21

## Slide 4: Actions from GSICS-EP-20(2/2)
Reference | Action Description | Actionee | Due date
A.GRWG.20190516.1 | GRWG to prepare the State of Observing System report. | GRWG Chair | EP-21
A.GRWG.20190516.2 | GRWG to organize the mini-conference on MW inter-calibration in 2020 GSICS annual meeting. | GRWG+GDWG chair | March 2020
A.GRWG.20190516.3 | GRWG to develop Terms of References for GRWG sub-groups. | GRWG Chair | EP-21
A.GDWG.20190516.1 | GDWG Chair to request CGMS Task Force on Satellite Data and Codes to review a proposal of adding SRF to International Data Subcategory of Common Table C-13 of WMO Manual on Codes for a coordination with WMO IPET-CM. | GDWG Chair | EP-21
A.GDWG.20190516.2 | GDWG Chair and Rob Roebeling (EUMETSAT) to review existing event logging database at each agency to ensure best practices are met. | GDWG Chair | EP-21
A.GDWG.20190516.3 | GDWG Chair to develop a procedure on updating Annual GSICS Calibration Report. | GDWG Chair | EP-21
A.GCC.20190516.1 | GCC to relax User Guide requirement and uncertainty for GSICS Products, if measurements come from operational maturity. | GCC Director | EP-21
A.GCC.20190516.2 | GCC with GRWG to demonstrate the QA4EO nature of selection criterion of reference Instrument to EP members. | GCC Director | EP-21
A.GCC.20190516.3 | GCC to draft the QA4EO based selection criterion of GSICS Deliverables for the endorsement by EP. | GCC Director | EP-21
A.GCC.20190516.4 | GCC to share the recommendations of EXP-5 on applying QA4EO processes in GSICS ( e.g. GPPA) with GSICS EP. | GCC Director | EP-21