## Slide 1: GSICS Data Working Group 03/31/2021
Kamaljit Ray (MOES)

## Slide 2: GDWG in the GSICS Framework
Slide curtesy Tim Hewison (EUMETSAT)
GDWG actively supports all aspects of GSICS activities
e.g . systems/metadata/products/wiki/GPPA
Detailed TOR here

## Slide 3: Terms of Reference of GDWG
Oversee and coordinate the data management activities of GSICS and advise the EP on questions related to GSICS data management including information delivery services;
b) Coordinate the specification of data and metadata formats and procedures for data exchange between the satellite agencies, the GSICS Processing and Research Centers (GPRCs), and the GSICS Coordination Center (GCC);
c) Support the specification of GSICS systems administered by the GCC; GSICS product catalogue, GSICS User Messaging Service, GSICS Wiki, etc.
d) Support the specification of GSICS systems and tools administered by the GSICS member and observer organizations.
e) Review and validate GSICS deliverables from a data management perspective;
f) Provide guidance to the contents and appearance of the GSICS websites maintained by WMO, GCC, and each GPRC;
g) Maintain cooperation with the research and development activities at the GPRCs and assist with their data management activities, as appropriate;
h) Provide the GSICS Executive Panel with a report on GSICS data management activities including recommendations as appropriate. Submit report three weeks prior to the annual meeting of the GSICS Executive Panel, and present it to the Panel.

## Slide 4
Recent GDWG activities
  Websites
    GSICS webpage at each agency
    Updating new WMO GSICS Portal
  GSICS Collaboration Servers
  Defining GSICS Conventions for new GSICS Deliverables
  Instrument Event Logging
  Annual Calibration Report (GRWG/GDWG Chair)
  Updating GSICS Plotting Tool
  Use of GitHub for collaborative work
  Action Tracking Tool (GCC+GDWG)
  Product Status Tool
  Google Colab Notebook
https://gsics.wmo.int/en/focal-points
GDWG Members as of March 2021
GDWG Membership

## Slide 5
A.GDWG.2019.9b.1: ISRO to work with KMA to upload their Plotting Tool code and configuration onto GDWG GitHub repository.
A.GDWG.2019.9b.2: ISRO to work with CMA to synchronise their RAC products between their servers to validate the synchronisation scripts.
A.GDWG.2019.9b.3: ISRO with support from EUMETSAT to update their THREDDS configuration such that it is in-line with the other collaboration services.
Action: A.GDWG.2019.9c.1 EUMETSAT to upload sync perl and shell scripts to GitHub.
Action: A.GDWG.2019.9p.1 Peter Miu (EUMETSAT) to create user guide for GSICS THREDDS.
Action: A.GDWG.2019.9p.2 NOAA to provide EUMETSAT the download script for review to see if this can be provided to users to improve the downloading of GSICS products.
Actions Status ( 2019)

## Slide 6: Minutes of GSICS Data Working Group Meeting held on 20th October,2020
KMA reported Establishment of the GitHub, Review of GPRC websites and building a plotting tool environment for internal system. KMA preparing the new KOMSAT products for GPPA (Jin Woo,KMA)
ESA has prepared a landing page website . Paolo mentioned that two brief papers have been submitted to the GSICS Newsletter and the launch of two updated portals for Cal/Val data: the EVDC (the ESA Atmospheric Validation Data Center https://evdc.esa.int/) and the CEOS Cal/Val Portal http://calvalportal.ceos.org/ (Paola,ESA)
IMD presented information on the INSAT-3D and INSAT-3DR and showed the mission objectives and described the satellites. Giri informed that Geophysical parameters derived from the satellites are available in HDF format and as per action points of last meeting timeline of upcoming satellites Landing pages with support of ISRO is being prepared and the progress will be intimated shortly to the group(Giri, IMD)
JMA provided an overview of GDWG activities with the current activities include support to event logging, and creation of GSICS products via the collaboration server.JMA products are on GSICS Collaboration server in EUMETSAT(Arata Okuyama,JMA)

## Slide 7: Minutes of GSICS Data Working Group Meeting held on 20th October,2020
NOAA also hosts the Coordination Center, so GDWG tasks also support GCC activities in addition to wider GSICS activities. Manik gave an overview of a tool recently developed by NOAA GDWG namely the GSICS Product Alert System. He showed members how to use the tool to receive information on GSICS , how to use the action tracker. NOAA GDWG would focus on applying Machine Learning to extract satellite information, building scripts to produce State of Observation Report and building pages and tools for connecting with the ISCCP and other user groups(Manik,NoAA)
Tim Hewison from EUMETSAT discussed how to roll out changes to GSICS conventions.
Rob Roebeling from EUMETSAT led the discussion on modifying and adding Landing Pages following the CGMS agreed format . He indicated that the WMO OSCAR webpage has been updated.

## Slide 8: Actions Status ( 2020)
Action Id | Item | Summary | Lead | Expected Completion | Actual Completion | Status
A.GDWG.20202010.1 |  | KMA to provide the members the process to get account and use the KMA GSICS github. | Hysook (KMA) | 3/1/20201 |  | Open
A.GDWG.20201020.3: |  | IMD to update to update GSICS on receiving of JPSS data at IMD | IMD | 3/1/2021 |  | open
A.GDWG.20201020.2 |  | R.K Giri (IMD) to provide updates on landing page to GDWG | R.K Giri | 3/1/2021 |  | open
A.GDWG.202010.20.5 |  | GDWG to review GRWG proposed product convention changes (A.GDWG.20201020.4) and revise convention accordingly | GDWG | 3/1/2021 |  | Open
A.GDWG.20200812.1: | http://gsics.atmos.umd.edu/bin/view/Development/20200812 | GDWG to review existing product THREDDS directory structure to make it easier for ISCCP-NG users to access products | Manik | 3/1/2021 |  | Open
A.GDWG.20200416.1 | http://gsics.atmos.umd.edu/bin/view/Development/20200416 | Manik Bali (NOAA) to coordinate GDWG to investigate developing scripts to generate contents of Annual Calibration Reports from GSICS Corrections. | Manik | 3/1/2021 |  | Open
A.GDWG.20201020.6 |  | WMO (Heikki) to nominate contact points to ensure that overlapping groups ( e.g IOGEO and ISCCP) can work in harmony with GSICS and strengthen Producer-User relationship. | WMO(Heikki) |  |  | Open
Show entries
Search:

## Slide 9: Plan for GDWG Break out Session 31 March Short session Starting 12:00 GMT
Suggested Topics
Data Working Group activities of each agency
Discussion on Users feedback on collaborative server directory structure.
Develop a procedure for updating Annual GSICS Calibration Reports.
GSICS Product Alert System and Support to GSICS ISCCP and IOGEO partnerships(Manik)
GSICS GitHub
How to roll out changes to the GSICS conventions in the future? - e.g., algorithm_version (Tim)
Scope of Instrument kiosk on GCC website

## Slide 10: Conclusion
Data working group is actively working on GSICS products and deliverables dissemination/standardization and acceptance.
Tools are being developed to connect with users of GSICS products and deliverables.
Collaboration Server/GPRC/Landing Pages are playing a crucial role in communicating the satellite monitoring to the community.
Tools, such as Google Colab/Product Status System, empower the users to dive into the products directly from the browser and usher in a collaborative development ecosystem in real time.

## Slide 11: Summary of links to GSICS tools
Bash script to download GSICS Data http://gsics.atmos.umd.edu/bin/view/Development/DownloadGSICSProducts
Series of notebooks to read, view and process GSICS Data and Deliverables from the browser in a collaborative ecosystem
  DCC Product notebook
    This notebook reads DCC products and plots and lists them
  GIRO SRF notebook
  GSICS Product RAC notebook and NRT notebook
3. Plotting Tool http://gsics.tools.eumetsat.int/plotter
4. GSICS Product Catalog: https://www.star.nesdis.noaa.gov/smcd/GCC/ProductCatalog.php
5. GSICS Product Status registration: Register here

## Slide 12: THANK YOU