## Slide 1: GDWG Actions Review
Masaya Takahashi (JMA)
CMA, CNES, ESA, EUMETSAT, ISRO, IMD, JAXA, JMA, KMA, NASA, NIST, NOAA, ROSCOSMOS, ROSHYDROMET, USGS, WMO

## Slide 2: GDWG Actions Summary
2018 Actions
  23 actions proposed
  16 actions have been already closed
  XX actions have feedback provided, they are in progress
  1 actions have been delayed
Older actions before 2017
  6 open actions
  2 closed
  1 in progress

## Slide 3
Action Id | Summary | Lead | Due Date | Completion
A.GDWG.2018.5a.1 | NOAA-GDWG( Bali) to propose updates to the Actions Tracker and GSICS User Messaging (GUM) service such that all GPRCs can use these applications. | NOAA | 2019-03-01 | 
A.GDWG.2018.5a.2 | Masaya Takahashi to upload the SRF format conversion script to GitHub. To be discussed at 6e. | JMA | 2019-03-01 | 
A.GDWG.2018.5b.1 | Masaya Takahashi to update minimumn requirements for GPRC website and inform WMO of the changes required for their website; addition of ISRO website. | JMA | 2019-03-01 | 2019-01-08
A.GDWG.2018.5c.1 | Peter Miu and Masaya Takahashi to organise a web meeting with ISRO and GDWG member to discuss bringing the ISRO server into the GSICS collaboration network. | EUM | 2019-03-01 | 2018-04-18
A.GDWG.2018.5c.2 | GDWG members (Jin Woo, Masaya Takahashi, Peter Miu, Thomas Xu and Manik Bali) to specify the plan and take care of progressing GSICS products through the GPPA (Lead: GDWG Chair). The goal is to being existing GSICS products into operations as soon as possible. | JMA | 2019-03-01 | 
2018 Actions (comments in blue)
Closed | In Progress | Delayed | Cancelled

## Slide 4
Action Id | Summary | Lead | Due Date | Completion
A.GDWG.2018.5c.3 | Peter Miu to specify a technical note to propose several methods for the implementation of passive and active GSICS products access service such as RSS on THREDDS. Technologies to consider should be available to all GPRC; RSS, EUMETSAT UNS, SMS, WeChat, … | EUM | 2019-03-01 | 
A.GDWG.2018.5c.4 | Peter Miu to update the GSICS product moving process on the EUMETSAT GSICS server to ignore products being uploaded with .TEMP, .temp, .etc. This is to avoid zero size products to be served to users. | EUM | 2019-03-01 | 2019-02-05
A.GDWG.2018.5c.5 | Peter Miu to implement a product upload timer to provide a report on how long it takes to received products from the product producers. | EUM | 2019-03-01 | 
A.GDWG.2018.5d.1 | CMA and EUMETSAT to work together to synchronise GSICS products across the servers. XU Zhe has reported that at GDWG web meeting on 2019-01-23 | CMA/EUM | 2019-03-01 | 2019-01-23
2018 Actions (comments in blue)
Closed | In Progress | Delayed | Cancelled

## Slide 5
Action Id | Summary | Lead | Due Date | Completion
A.GDWG.2018.5d.2 | CMA to check if their NetCDF format checking tool can be shared in GSICS. CMA GDWG confirm can share NetCDF format checking tool's script | CMA/EUM | 2019-03-01 | 2019-03-01
A.GDWG.2018.5j.1 | Rob Roebeling to make a proposal for the WMO OSCAR/Space Instrument Pages for review by the GDWG so that a recommendation can be presented to WMO to improve the usability of these pages. | EUM | 2019-03-01 | 2018-09-18
A.GDWG.2018.5j.2 | GDWG members to take the event logging white paper to see whether their organisation can do with regards to implementing such a system and report back to GDWG. | JMA | 2019-03-01 | 2018-04-30
A.GDWG.2018.5j.3 | GDWG Chair/Vice Chair to prepare a reply to “R45.05: Calibration Events Logging Task Team be folded formed under GSICS as a task team” for CGMS-46. Reply shall be sent to Rob (team lead) for review and presented to the EP by GDWG chair. EP chair shall present the result to CGMS-46 in the dedicate GSICS presentation. | JMA | 2019-03-01 | 2018-06-01
A.GDWG.2018.8a.1 | Masaya Takahashi to update action identifier definition for GSICS-EP meetings. | JMA | 2019-03-01 | 2018-06-01
2018 Actions (comments in blue)
Closed | In Progress | Delayed | Cancelled

## Slide 6
Action Id | Summary | Lead | Due Date | Completion
A.GDWG.2018.8a.2 | NOAA-GDWG (Manik Bali) to summarize action tracking tool on the Wik | NOAA | 2019-03-01 | 2019-01-22
A.GDWG.2018.8a.3 | NOAA-GDWG (Manik Bali) to summarise current status of GSICS Wiki (e.g. server configuration, system requirements) and inform to WMO | NOAA | 2019-03-01 | 
A.GDWG.2018.8b.1 | Zhe Xu to provide their Data needs to GDWG chair for presenting to EP chair to present to CGMS to see if agencies can provision of support to this data exchange request. Will be discussed in annual meeting 2019 | CMA | 2019-03-01 | 
A.GDWG.2018.8f.1 | Ninghai Sun to share their ICVS user manual with the GDWG members when it becomes available. | NOAA | 2019-03-01 | 
A.GDWG.2018.8h.1 | GDWG Chair to propose a refinement of GDWG ToR to GSICS-EP. | JMA | 2019-03-01 | 2018-06-01
A.GDWG.2018.8i.1 | Peter Miu to contact ISRO to discuss future collaboration through visiting data management expert exchange. | EUM | 2019-03-01 | 2019-02-05
A.GDWG.2018.8k.1 | Masaya Takahashi to circulate GDWG Fact Sheet to GDWG members to get feed backs and report to EP. | JMA | 2019-03-01 | 2018-06-01
2018 Actions (comments in blue)
Closed | In Progress | Delayed | Cancelled

## Slide 7
Action Ref. | Description | Lead | Due date | Completion
GDWG_14.15 | IMD to update their website to provide GSICS information. This will be provided on the WMO for inclusion into their website. | IMD | 2015-06-01 | 
GDWG_2016.5b.1 | JMA to include invalid_hours in the agreed conventions once the time format has been checked that it follows ISO 8601 format. Delayed due to limited resources. | JMA | 2016-07-31 | 
A.GDWG.2017.5a.2 | CMA to add a link to the ATBD on their GSICS website. | CMA | 2018-03-31 | 
A.GDWG.2017.5a.8 | Peter Miu to document formats of the GEOLEOIR products (example high level definition of the GIRO I/O [EUM/TSS/TEN/14/753739]). | EUM | 2017-09-30 | 
A.GDWG.2017.5a.9 | Peter Miu to contact Unidata to see if branches can indicate data is available, hyperlink to logo and home at top of screen. | EUM | 2017-04-30 | 
A.GDWG.2017.5c.1 | Jordan Yao to confirm whether their THREDDS configuration follows the latest one which was proposed by EUMETSAT. | NOAA | 2017-12-31 | 
Open Actions before 2017 (comments in blue)
Closed | In Progress | Delayed | Cancelled

## Slide 8
Action Id | Summary | Lead | Due Date | Completion
A.GDWG.2017.6a.1 | GDWG members to consider to add “Calibration related documents” on their landing pages. ROSHYDROMET launched the page. | EUM | 2017-12-31 | 2018-12-31
A.GDWG.20171108.1 | Manik to provide script that can check uptime of THREDDS servers and product updates on the THREDDS servers that are shared via the collaboration server. | NOAA | 2018-03-01 | 
A.GDWG.20171108.3 | Rob to update the URLs of all the instrument event logging pages and each agency to confirm the URLs. ROSHYDROMET launched the page. | EUM | 2018-03-01 | 2018-12-31
2017 Actions (comments in blue)
Closed | In Progress | Delayed | Cancelled